## Overall status (date)
Team Name EEJ1
Case Study Name Hadoop Cluster Setup
Date 6/27/2016 -7/01/2016
Overall Status (On Track / Delayed / At Risk )
At Risk
Accomplishments since last evaluation
1) Benchmarking of hadoop environment
2) Preparing Azkaban workflows for:
- Listing all movies and number of ratings
- Listing all the User with Maximum,Minimum and Average ratings they have given against any movie
3) Preparing Oozie workflows for:
- Listing all movies and number of ratings
- Listing all the User with the max,min,average ratings they have given against any movie.
4) Test kerberos security
Targets for this week
Yet to decide in sprint planning meeting.
Impediments
Learning this week
Evaluator's Comments

## Detailed Status
Story ID | Task Details | Owner(s) | Status
US040 | I want to understand/setup ELK stack | Sudesh & Pradeep | In Progress
US055 | I want to benchmark the Hadoop Environment -So that I can know how the potential performance bottlenecks and resource utilization | Shashwat & Dilip | Done
US005 | I want to prepare 1 Azkaban workflow to list all the movies and the number of ratings | Deepti & Santosh | Done
US006 | I want to prepare 1 oozie workflow to list all the users and the number of ratings they have done for a movie | Sanchita | Done
US036 | I want to do Kerberose Security Testing -To ensure the security is applied to the environment - Understanding Kerberos security - Perform Kerberose Security Testing | Dilip & Abhishek | Done
US037 | I want to do HA testing -So that I am able to test the failover testing and fault tolerance of the system - Add test cases for HA testing - Perform HA testing | Dilip & Abhishek | Done
US044 | I want to explore Hive view in Ambari for Query & Database management - so that user can author and execute queries in the Query Editor | Gagandeep | Done
US013 | I want to prepare 1 Azkaban workflow to list all the User with : - Maximum ratings they have given against any movie - Minimum ratings they have given against any movie - Average ratings they have given against any movie | Gagandeep | Done
US012 | I want to prepare 1 oozie workflow to list all the User with the max,min,average ratings they have given against any movie | Rupika | In- Progress
US069 | Adding a new host to our cluster as replacement to the crashed one and to sync all parameters. | Sudesh | Done
US014 | As a Dev I want to prepare 1 oozie workflow to list all the Movies with the max,min,average ratings given by any user So that I can list all the Movies with the max,min,average ratings given by any user. | OM | Done
US010 | I want to prepare 1 oozie workflow to list all the Users who have rated the movies (Users who have rated atleast one movie) So that I can list all the Users who have rated the movies (Users who have rated atleast one movie). | OM | In- Progress
US057 | I want to test Azkaban workflow which list all the movies and the number of ratings | Ravi | Done
Note on D1: :not started , in progress , completed

## Retrospective Notes
Date - 06/21/2016
Sprint 3
Name | What went well | What did not go well
Shashwat Sharma | Installation and setting up of Ganglia Monitoring tool
Ravi Bhardwaj
Rupika Mahajan | Completed writing hive queries for use cases
Dilip Dave
Pradeep Chand Nailwal | Sprint Goal is achieved
Sudesh Shettigar | Installation and setting up of Nagios Monitoring tool | Since one of the host hosting Kerberos had crashed hence could not add all components for rmonitoring
Santosh Kumar Jha
Deepti Agrawal | Sprint Goal is achieved
Om Prakash Soni
Sanchita Mishra | Through better task management and coordination , Team achieved the sprint goals. | Review PPT with incorrect info was sent before Evaluation meeting.
Gagandeep Singh Panesar | Reference Movie lens data added successfully into Hive. Also completed Use Case #1 | Wasn’t able to run Hive queries from Ambari Gui. Will work in this sprint for exploration & fixing the same.
Abhishek Parihar | Sprint Goal is achieved
​Om Prakash Soni | Able to execute Pig script and hive sqls over movie data. Succesfully uploaded data into hive after processing through Pig. | ​Could understand the use cases properly. Need more clarification on that.