## Overall status (date)
Team Name EEJ1
Case Study Name Hadoop Cluster Setup
Date 6/17/2016 -6/24/2016
Overall Status (On Track / Delayed / At Risk )
On Track
Accomplishments since last evaluation
1) Adding a new host to our cluster as replacement to the crashed one and to sync all parameters.
2) Explore hive view in Ambari & execute Hive queries from Ambari.
Targets for this week
1) Benchmarking of hadoop environment
2) Preparing Azkaban workflows for:
- Listing all movies and number of ratings
- Listing all the User with Maximum,Minimum and Average ratings they have given against any movie
3) Preparing Oozie workflows for:
- Listing all movies and number of ratings
- Listing all the User with the max,min,average ratings they have given against any movie.
4) Test kerberos security
Impediments
Learning this week
Evaluator's Comments

## Detailed Status
Story ID | Task Details | Owner(s) | Status
US040 | I want to understand/setup ELK stack | Sudesh & Pradeep | In Progress
US055 | I want to benchmark the Hadoop Environment -So that I can know how the potential performance bottlenecks and resource utilization | Shashwat & Dilip | In Progress
US005 | I want to prepare 1 Azkaban workflow to list all the movies and the number of ratings | Deepti & Santosh | In Progress
US006 | I want to prepare 1 oozie workflow to list all the users and the number of ratings they have done for a movie | Sanchita | In Progress
US036 | I want to do Kerberose Security Testing -To ensure the security is applied to the environment - Understanding Kerberos security - Perform Kerberose Security Testing | Dilip & Abhishek | In- Progress
US037 | I want to do HA testing -So that I am able to test the failover testing and fault tolerance of the system - Add test cases for HA testing - Perform HA testing | Dilip & Abhishek | In- Progress
US044 | I want to explore Hive view in Ambari for Query & Database management - so that user can author and execute queries in the Query Editor | Gagandeep | Done
US013 | I want to prepare 1 Azkaban workflow to list all the User with : - Maximum ratings they have given against any movie - Minimum ratings they have given against any movie - Average ratings they have given against any movie | Gagandeep | In-Progress
US012 | I want to prepare 1 oozie workflow to list all the User with the max,min,average ratings they have given against any movie | Rupika | In- Progress
US069 | Adding a new host to our cluster as replacement to the crashed one and to sync all parameters. | Sudesh | Done
US014 | As a Dev I want to prepare 1 oozie workflow to list all the Movies with the max,min,average ratings given by any user So that I can list all the Movies with the max,min,average ratings given by any user. | OM | In- Progress
US010 | I want to prepare 1 oozie workflow to list all the Users who have rated the movies (Users who have rated atleast one movie) So that I can list all the Users who have rated the movies (Users who have rated atleast one movie). | OM | Not- Started
US057 | I want to test Azkaban workflow which list all the movies and the number of ratings | Ravi | In- Progress
Note on D1: :not started , in progress , completed

## Retrospective Notes
Date - 06/21/2016
Sprint 3
Name | What went well | What did not go well
Shashwat Sharma | Installation and setting up of Ganglia Monitoring tool
Ravi Bhardwaj
Rupika Mahajan | Completed writing hive queries for use cases
Dilip Dave
Pradeep Chand Nailwal | Sprint Goal is achieved
Sudesh Shettigar | Installation and setting up of Nagios Monitoring tool | Since one of the host hosting Kerberos had crashed hence could not add all components for rmonitoring
Santosh Kumar Jha
Deepti Agrawal | Sprint Goal is achieved
Om Prakash Soni
Sanchita Mishra | Through better task management and coordination , Team achieved the sprint goals. | Review PPT with incorrect info was sent before Evaluation meeting.
Gagandeep Singh Panesar | Reference Movie lens data added successfully into Hive. Also completed Use Case #1 | Wasn’t able to run Hive queries from Ambari Gui. Will work in this sprint for exploration & fixing the same.
Abhishek Parihar | Sprint Goal is achieved
​Om Prakash Soni | Able to execute Pig script and hive sqls over movie data. Succesfully uploaded data into hive after processing through Pig. | ​Could understand the use cases properly. Need more clarification on that.