## Overall status (date)
Team Name EEJ1
Case Study Name Hadoop Cluster Setup
Date 6/10/2016 -6/17/2016
Overall Status (On Track / Delayed / At Risk )
On Track
Accomplishments since last evaluation
1. Created 4 node cluster using Ambari
2. installed hadoop,hive,pig,oozie,zookeeper
3. Ganaglia and Nagios is installed
4. Gather reference movie lens data and pushed it on HDFS.
5.Create the HIVE table for Movie lense data
Targets for this week
Nagios and Ganglia to understand its advantages and limitations over each other.
Manual Installation of components like Nagios, Ganglia.
Explore refining data using PIG - Exploration for storing refined data from PIG to HIVE." - Exploration for storing refined data from PIG to file.
Process Sample data through pig and data is pushed to the hive table
setup kerborse
Ranger setup
Impediments
Due to one of the nodes hard drive failure, we are blocked
Learning this week
Evaluator's Comments

## Detailed Status
Task ID | Description | Owner | ETA | Impediments
US018 | I want to explore Nagios and Ganglia to understand its advantages and limitations over each other. | Shashwat & Sudesh | Done
US041 | I want to do manual Installation of components like Nagios, Ganglia. | Shashwat & Sudesh | Done
| Setting up monitor console using Nagios/Ganglia to monitor CPU, Memory, HDP services and parameters | Shashwat & Sudesh | Blocked
US051 | I want to explore refining data using PIG - Exploration for storing refined data from PIG to HIVE. | Om | Done
| - Exploration for storing refined data from PIG to file. | Gagandeep | Done
US052 | I want to gather reference movie lens data - Gather reference data for movie lens | Om & Gagandeep | Done
US053 | I want to refine data using PIG - Identify data to be processed into HIVE table. (Fields required from raw data) - Creating HIVE tables for refined data | Om & Gagandeep | Done
US068 | I want to add refined data into HIVE tables - Add refined data into HIVE tables. - Verfiy presence of data added into tables (MOVIES, USERS, RATINGS) | Om & Gagandeep | Done
US039 | Environment Testing -Hadoop Installation -Hive Installation | Abhishek | Done
| Environment Testing: Pig Installation -Verify the installion of PIG on all components Yarn Installtion Verify the installation of YARN on all components Nagios Installation -Verify the installation of Nagios Agent Ganglia Installation -Verify the installation of Ganglia | Dilip | Done
| Environment Testing: - Oozie Installation - Spark Installation - Ranger insatallation | Ravi | Done
US004 | Explore more on oozie workflow | Sanchita & Santosh | Done
| prepare oozie workflow to list all the movies and the number of ratings | Sanchita & Santosh | In Progress
1) Creating workflow xml - Done
2) Creating Hive query for table creation -Done
3) Create Hive query for data loading - In Progress
4) Job Configuration - Done
US054 | Create cluster through Ambari. (Done) Install services like PIG,HIVE through Ambari. (Done) Run Hive Scripts on installed Hive. (Done) | Deepti & Rupika | Done
US021 | Create Movie database and prepare simple hive query. | Pradeep | Done

## Retrospective Notes
Date
Positive Points during the Sprint / Cycle | Not so positive Points during the Sprint / Cycle | Areas of improvement - that team should work on
4 Node Cluster Deployment, Ranger installation, Enabling HA on Namenode and Resource Manger and enabling Kerbrose security went fine. | No issues faced in sprint 2 task. | Team should fill the sheet on daily basis, for efforts they put and reaming efforts of their task.
Create Test Strategy Doc | Better management of task allocation is needed | Need to fill scrum sheet on daily basis
| Make sure all the team members should attend weekly calls & DSM. | Still improvement is needed on team participation in DSm and other meetings.
Created Test plan docand shared with team
4 Node Cluster Deployment, Ranger installation, Enabling HA on Namenode and Resource Manger and enabling Kerbrose security went fine.
Ambari installation has been completed.
Learnt Apache Pig details and completed my assigned tasks
Team is more involved in sprint 2 as compared to sprint 1.
Successfully completed one sample workflow using HIVE.
Updated Test cases and shared with team