## Overall status (date)
Team Name: EEJ1
Case Study Name: Hadoop Cluster Setup
Date: 7/04/2016 -7/15/2016
Overall Status (On Track / Delayed / At Risk ): On Track
Accomplishments since last evaluation
1) Able to refine the User Stories for final case study delivery
2) Team working in collabration irrespective of tasks to achieve the sprint goals
3) Individuals started taking ownership of the other tasks on their own
4) Team was able to spend extra time to recreate 2 nodes when cluster unexpetedly went down
5) Tasks on track to finish in the current sprint
Targets for this week
4 Sprint goals finalized already , demo of 6 worflows planned for next week's evaluation
Impediments
Cluster went down for couple of days, which impacted most of the user stories
Unplanned effors were made to restore the cluster back to its original state
Learning this week
Evaluator's Comments

## Detailed Status
SPRINT-05
Story ID | Task Details | Estimate (Hours) | Owner(s) | Status
US040 | I want to understand/setup ELK stack | 18 | Sudesh & Pradeep | Done
ELK had to be setup again as the node on which it was running earlier had disk failure
US012 | I want to prepare 1 oozie workflow to list all the User with the max,min,average ratings they have given against any movie | 16 | Rupika | In- Progress
US010 | I want to prepare 1 oozie workflow to list all the Users who have rated the movies (Users who have rated atleast one movie) So that I can list all the Users who have rated the movies (Users who have rated atleast one movie). | 14 | OM & Gagandeep | Done
US049 | #Installation of Apache Spark #Exploration of Apache spark to implement 1 workflow of Spark -Explored Apache Spark -Scala | 12 | Sudesh & Pradeep | Done
US045 | List all the Movie IDs which have been rated (Movie Id with at least one user rating it) (Azkaban) | 7.5 | Deepti | Done
US047 | List all the users and the number of ratings they have done for a movie (Azkaban) | 15 | Santosh | In progress
US065 | I want to test Azkaban workflow which list all the User with the max,min,average ratings they have given against any movie | 12 | Dilip | In- Progress
US066 | I want to test oozie workflow which list all the Movies with the max,min,average ratings given by any user | 7 | Ravi | In-Progress
US056 | I want to test oozie workflow to list all the Users who have rated the movies (Users who have rated atleast one movie) So that I can list all the Users who have rated the movies (Users who have rated atleast one movie). | 15 | Abhishek | In- Progress
US017 | I want to set up git and project structure . | 7.5 | Deepti | Done
US043 | I want to create monitoring configurations and weekly health reports | 20 | Shashwat | In - Progress
US022 | I want to create document for Solution architecture for setting up cluster | 16 | OM & Gagandeep | Done
US070 | Re-setting up of Cluster on account of 2 Nodes disk failure. Setup entire 4 node cluster again with Namenode HA,Resource Manger HA and Kerberos enabled | 10 | Sudesh | Done
Note on E2: :not started , in progress , completed

## Retrospective Notes
Sprint 4
Name | What went well | What did not go well | Things to improve upon
Shashwat Sharma | Sprint was successful , team is able to complete their task on weekend.
Ravi Bhardwaj | Able to achieve sprint goals. | Could not provide more time due to important project work
Rupika Mahajan | ​Sprint goal achieved | Could not provide more time due to important project work | Need to explore more on technologies
Dilip Dave | Cluster was not working well with Kerbrose, but issue addressed on time by Sudesh which prevented Security testing US from spilling over | Delay in few US due to unavailablity of few team members in their respective projects | Dedicate extra time to complete the US in hand irrespective of project/client work
Pradeep Chand Nailwal | Able to achieve sprint goals.
Sudesh Shettigar | ELK Setup was done, but issues observed on configuraiton side | It dealyed the US completion in the sprint, US spilled over
Santosh Kumar Jha | I was able to complete my user stories on time | Could not setup Azkaban on shared cluster due to hive version compatibility
Deepti Agrawal | Team is able to complete Sprint goals |  | Team can Explore more on the technology
Om Prakash Soni
Sanchita Mishra | On leave | On leave | On leave
Gagandeep Singh Panesar | Sprint goal achieved
Abhishek Parihar | Completed HA testing | Delayed due to cluster issue
What did not go well? | Some cluster issues were observerd lately when the sprint was about to end which impacted multiple stories delivery on time
What could be improved? | Need regular monitoring and maintenance of cluster to avoid cluster issues