## ExecutionSummary
Sprint Wise Test Case Summary
Sprint 01 Summary |  |  | Sprint 02 Summary |  |  | Sprint 03 Summary |  | Sprint 04 Summary |  | Sprint 05 Summary |  | Sprint 06 Summary
Status | TestCount |  | Status | TestCount |  | Status | TestCount | Status | TestCount | Status | TestCount | Status | TestCount
Pass | 0 |  | Pass | 0 |  | Pass | 40 | Pass | 13 | Pass | 25 | Pass | 102
Fail | 0 |  | Fail | 0 |  | Fail | 0 | Fail | 0 | Fail | 0 | Fail | 0
Blocked | 0 |  | Blocked | 0 |  | Blocked | 0 | Blocked | 0 | Blocked | 0 | Blocked | 0
Not Run | 40 |  | Not Run | 13 |  | Not Run | 38 | Not Run | 34 | Not Run | 33 | Not Run | 0
Total TCs | 40 |  | Total TCs | 53 |  | Total | 78 | Total TCs | 87 | Total | 111 | Total TCs | 156
Sprint-06 Details (Cycle#1 and Cycle#2)
DataBase Queries For Testing Data Execution Summary | [5 empty] | SmokeTest Suite Summary
Summary Cycle 1 |  |  | Summary Cycle 2 |  |  | Summary Cycle 1
Status | TestCount |  | Status | TestCount |  | Status | TestCount
Pass | 23 |  | Pass | 24 |  | Pass | 45
Fail | 1 |  | Fail | 0 |  | Fail | 0
Blocked | 0 |  | Blocked | 0 |  | Blocked | 0
Not Run | 0 |  | Not Run | 0 |  | Not Run | 0
Total TCs | 24 |  | Total TCs | 24 |  | Total TCs | 45
Sprint | #TCs Executed | Pass | Fail | Not Run | # Total TCs
Sprint 01 | 0 | 0 | 0 | 40 | 40
Sprint 02 | 0 | 0 | 0 | 13 | 53
Sprint 03 | 40 | 40 | 0 | 38 | 78
Sprint 04 | 13 | 13 | 0 | 34 | 87
Sprint 05 | 25 | 25 | 0 | 33 | 111
Sprint 06 | 102 | 102 | 0 | 0 | 156
Sprint | #TCs Executed | Pass | Fail | Not Run | New TCs | # Total TCs
Sprint 01 | 0 | 0 | 0 | 40 | 40 | 40 | [7 empty] | 78
Sprint 02 | 0 | 0 | 0 | 13 | 13 | 53
Sprint 03 | 40 | 40 | 0 | 38 | 25 | 78
Sprint 04 | 13 | 13 | 0 | 34 | 9 | 87
Sprint 05 | 25 | 25 | 0 | 33 | 24 | 111
Sprint 06 | 102 | 102 | 0 | 0 | 45 | 156
Sprint | #TCs Executed | Pass | Fail | Fixed | Not Run | # Total TCs
Sprint 01 | 0 | 0 | 0 | 0 | 40 | 40
Sprint 02 | 0 | 0 | 0 | 0 | 13 | 53
Sprint 03 | 40 | 40 | 1 | 1 | 38 | 78
Sprint 04 | 13 | 13 | 1 | 1 | 34 | 87
Sprint 05 | 25 | 25 | 0 | 0 | 33 | 111
Sprint 06 | 102 | 102 | 3 | 3 | 0 | 156

## TestCases
User Story | TestCase ID | Feature | Objective | Priority | Pre-Requisite | Steps | Expected Result | Actual Result | Status | Sprint 01 | Sprint 02 | Sprint 03 | Sprint 04 | Sprint 05 | Sprint 06 | DefectID | Comments
Environment Testing:
US039 | US039_TC001 | Environment Testing | To Verify that all 4 ubuntu machines are accessible from EETeamJ1 users. | High | 4 Ubuntu-Machines provided to EETeamJ1 team | Login to all 4 ubuntu machines by using their credentials | Users(EETeamJ1 Team) should be able to Login into all 4 ubuntu machines by using their credentials | Users are able to Login into all 4 ubuntu machines by using their credentials |  | TC Created |  | Pass
US039 | US039_TC002 | Environment Testing | To Verify that Ubuntu OS version should be 14.04 in all 4 ubuntu machines. | High | Machines are accessible | Command: lsb_release -a Reason for not using latest OS version: Ubuntu 15 comes with python 2.7.9 and it has issues in performing certificate validation as reported by Horton works site | Ubuntu OS version should be 14.04 in all 4 ubuntu machines. | Ubuntu OS version is 14.04 in all 4 ubuntu machines. |  | TC Created |  | Pass |  |  |  |  | Ubuntu 15 comes with python 2.7.9 and it has issues in performing certificate validation as reported by Horton works site
US039 | US039_TC003 | Environment Testing | To verify java installed successfully | High | Machines are accessible | execute command on console: java -version | Java installation should successfully completed | Java installation is successfully completed |  | TC Created |  | Pass
US039 | US039_TC004 | Environment Testing | To Verify that Ambari setup is successfully completed on ubuntu machines | High | Java should be installed | Access Ambari GUI | Ambari setup should be successfully completed on ubuntu machines | Ambari setup is successfully completed on ubuntu machines |  | TC Created |  | Pass
US039 | US039_TC005 | Environment Testing | To Verify that user is able to access and login Ambari GUI dashboard. | High | Ambari installation | Ambari GUI dashboard: http://172.26.60.16:8080/#/login Usename: admin Password: admin | user should be able to access and login Ambari GUI dashboard. | user is able to access and login Ambari GUI dashboard by using following credentials: http://172.26.60.16:8080/#/login Usename: admin Password: admin |  | TC Created |  | Pass
US039 | US039_TC006 | Environment Testing | To Verify that Hadoop installation is configured successfully on all 4 nodes by using Ambari. | High | Multi-node Hadoop cluster environment | Login to Ambari GUI dashboard and verify. | Hadoop installation should be configured successfully on all 4 nodes by using Ambari. | Hadoop installation is configured successfully on all 4 nodes by using Ambari. |  | TC Created |  | Pass
US039 | US039_TC007 | Environment Testing | Verify that Hadoop Daemons are successfully started. | High | Hadoop installation successfully completed | start-all.sh : Used to start hadoop daemons all at once. Issuing it on the master machine will start the daemons on all the nodes of a cluster. OR start-dfs.sh and start-yarn.sh : Same as above but start HDFS and YARN daemons separately on all the nodes from the master machine. It is advisable to use these commands now over start-all.sh | Hadoop Daemons should be successfully started. | Hadoop Daemons are successfully started. |  | TC Created |  | Pass
US039 | US039_TC008 | Environment Testing | Verify that Hadoop Daemons are successfully stopped. | High | Hadoop installation successfully completed | stop-all.sh : Used to stop hadoop daemons all at once. Issuing it on the master machine will stop the daemons on all the nodes of a cluster. Deprecated as you have already noticed. OR stop-dfs.sh and stop-yarn.sh : Same as above but stop HDFS and YARN daemons separately on all the nodes from the master machine. It is advisable to use these commands now over stop-all.sh | Hadoop Daemons should be successfully stopped. | Hadoop Daemons are successfully stopped. |  | TC Created |  | Pass
US039 | US039_TC009 | Environment Testing | To Verify that Hive setup configured successfully through Ambari. | High | Hive installation/configuration successfully completed | Login to box, Login to hive setup by 'sudo su - hive' command then use 'hive' command to enter hive DB Execute Hive queries | Hive setup should be configured successfully through Ambari. | Hive setup configured successfully through Ambari. |  | TC Created |  | Pass
US039 | US039_TC010 | Environment Testing | To Verify that HDFS setup configured successfully through Ambari.(Hadoop Installation) | High | Hadoop should be installed into the environment | Given I login as admin to Ambari And I navigate to HDFS And I see the "Summary" | HDFS setup should be installed successfully through Ambari. | HDFS setup installed successfully through Ambari. |  | TC Created |  | Pass
US039 | US039_TC011 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I navigate to YARN And I see the "Summary" And I should see the following "App Timeline Server , Standby ResourceManager , Active ResourceManager, NodeManagers, NodeManagerStatus" | All should be in "Started" status | All were showing "Started" and "Active" status |  | TC Created |  | Pass
US039 | US039_TC012 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I navigate to YARN And I see the "Summary" And I see "YARN Clients" And I click on the above link And I am able to see all the nodes | All the nodes should be up and running | All clients running |  | TC Created |  | Pass
US039 | US039_TC013 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I navigate to YARN And I navigate to "Heatmap" And I see different metric for all the nodes From the drop down select different metric | On changing the "Select Metric" drop down, the grapsh should get changed and show the status of nodes as per the selected metric | Nodes were showing data as per the metric selected |  | TC Created |  | Pass
US039 | US039_TC014 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I navigate to YARN And I navigate to "Config" And I see "Settings" and "Advanced" tab On Settings various settings like Memory, Container, YARN Features, CPU etc. will be visible | Change the settings and the changes should reflect | Done the changes in the settings, and changes were visible after the restart of the nodes |  | TC Created |  | Pass
US039 | US039_TC015 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I navigate to YARN And I navigate to "Config" And I see "Settings" and "Advanced" tab On Advanced tab various config change parameters, paths, values will be visible | Change the various settings and it should get reflected in the cluster | Done the changes in the settings, and changes were visible after the restart of the nodes |  | TC Created |  | Pass
US039 | US039_TC016 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I navigate to YARN And I see "Service Actions" button And I click on "STOP" | All components running YARN should be stopped, and alerts should be generated if maintanence mode is not selected | One of the node was not getting stopped |  | TC Created |  | Pass |  |  |  | DE003
US039 | US039_TC017 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I navigate to YARN And I see "Service Actions" button And I click on "Refresh YARN Capacity Scheduler" | A background job will be created by the name "Refresh YARN Capacity Scheduler" | Background job created |  | TC Created |  | Pass
US039 | US039_TC018 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I navigate to YARN And I see "Service Actions" button And I click on "Restart All" | A background job will be created by the name "Restarting YARN components" | Background job created for YARN restart |  | TC Created |  | Pass
US039 | US039_TC019 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I navigate to YARN And I see "Service Actions" button And I click on "Run Service Check" | A background Ops job will be created | A job is created |  | TC Created |  | Pass
US039 | US039_TC020 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I navigate to YARN And I see "Service Actions" button And I click on "Turn On Maintenance Mode" | YARN should enter into Maintenance Mode with the Logo of YARN be changed into Maintenance mode logo, and no alerts should get suppressed during this mode | Maintenance mode was on, with no alerts generated when Stop, Start of services or config change was done in YARN |  | TC Created |  | Pass
US039 | US039_TC021 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I navigate to YARN And I see "Service Actions" button And I click on "Turn Off Maintenance Mode" | YARN should exit the maintenance mode and the logo should be Green Tick with active status and alerts should generate for every action | Maintenance mode was switched off and alerts were generated |  | TC Created |  | Pass
US039 | US039_TC022 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I am on Ambari Dashboard page And I move cursor to top right side of the dashboard on a 9 square icon next to "Admin" And I see "YARN Queue Manager" | YARN Queue Manager should be visible in the dropdown | YARN Queue Manager is visible |  | TC Created |  | Pass
US039 | US039_TC023 | Environment Testing | To Verify that YARN is installed , configured ans is running successfully | High | YARN should be installed into the environment | Given I login as admin to Ambari And I am on Ambari Dashboard page And I move cursor to top right side of the dashboard on a 9 square icon next to "Admin" And I see "YARN Queue Manager" And I click on "YARN Queue Manager" And I click on "Add Queue" | On clicking on "Add Queue" button I should be able to add new queue | New queue should be visible after adding the mandatory details |  | TC Created |  | Pass
US039 | US039_TC024 | Environment Testing | To Verify that PIG is installed , configured ans is running successfully | High | PIG should be installed into the environment | Given I login as admin to Ambari And I am on Ambari Dashboard page And I see "Pig" on the left pan of Ambari Dashboard | Pig should be visible | Pig is visible |  | TC Created |  | Pass
US039 | US039_TC025 | Environment Testing | To Verify that PIG is installed , configured ans is running successfully | High | PIG should be installed into the environment | Given I login as admin to Ambari And I am on Ambari Dashboard page And I see "Pig" on the left pan of Ambari Dashboard And I click on Pig And I am on Pig Summary Page And I see a link "Pig Clients" And I click on Pig Clients | All the nodes with Pig clients will be visible here, all compoents should be in "Green" | All the components are Green |  | TC Created |  | Pass
US039 | US039_TC026 | Environment Testing | To Verify that PIG is installed , configured ans is running successfully | High | PIG should be installed into the environment | Given I login as admin to Ambari And I am on Ambari Dashboard page And I see "Pig" on the left pan of Ambari Dashboard And I click on Pig And I am on Pig Summary Page And I see a link "Pig Clients" And I click "Service Actions" And I select "Run Service Check" | A background job will be created which will give run service check on all the nodes | Pig service was TC Createdning on 1 node |  | TC Created |  | Pass
US039 | US039_TC027 | Environment Testing | To Verify that PIG is installed , configured ans is running successfully | High | PIG should be installed into the environment | Given I login as admin to Ambari And I am on Ambari Dashboard page And I see "Pig" on the left pan of Ambari Dashboard And I click on Pig And I am on Pig Summary Page And I see a link "Pig Clients" And I click "Service Actions" And I select "Refresh Configs" | A background job will be created which will update config on all the nodes running PIG service | Job was created |  | TC Created |  | Pass
US039 | US039_TC028 | Environment Testing | To Verify that PIG is installed , configured ans is running successfully | High | PIG should be installed into the environment | Given I login as admin to Ambari And I am on Ambari Dashboard page And I see "Pig" on the left pan of Ambari Dashboard And I click on Pig And I am on Pig Summary Page And I see a link "Pig Clients" And I click "Service Actions" And I select "Download Client Configs" | A config file ".tar.gz" will be downloaded with all the config files related to PIG | tar.gz files was downloaded |  | TC Created |  | Pass
US039 | US039_TC029 | Environment Testing | To verify Nagios is installed and configured successfully | High | Nagios should be installed | Login to Nagios using the URL http://impetus-i0095.impetus.co.in/nagios/ (nagiosadmin/eeteamj1) | Nagios Core homepage will be opened, check host status , All hosts should be visible, services should be visible in the service seciton | All hosts are be visible with service information |  | TC Created |  | Pass
US039 | US039_TC030 | Environment Testing | To verify Ganglia is installed and configured successfully | High | Ganglia should be installed | Login to Ganglia using the URL http://impetus-i0161/ganglia/ | Ganglia Grid will be opened | All the hosts visible with service status information of each host |  | TC Created |  | Pass
US039 | US039_TC031 | Environment Testing | To verify that NameNode host is up and running. | High | 4 node cluster configured successfully | Execute jps command on console to know whether NameNode is up and running | NameNode host should be up and running. | NameNode host is up and running. |  | TC Created |  | Pass
US039 | US039_TC032 | Environment Testing | To verify that Secondary NameNode host is up and running. | High | 4 node cluster configured successfully | Execute jps command on console to know whether SNN is up and running | Secondary NameNode host should be up and running. | Secondary NameNode host is up and running. |  | TC Created |  | Pass
US039 | US039_TC033 | Environment Testing | To verify that all DataNodes are up and running | High | 4 node cluster configured successfully | Execute jps command on console to know whether DataNodes is up and running | All DataNodes host should be up and running. | All DataNodes hosts are up and running. |  | TC Created |  | Pass
US039 | US039_TC034 | Environment Testing | To verify that NodeManager are up and running | High | 4 node cluster configured successfully | Execute jps command on console to know whether NodeManager is up and running | NodeManager host should be up and running. | NodeManager host is up and running. |  | TC Created |  | Pass
US039 | US039_TC035 | Environment Testing | To verify that ResourceManager are up and running | High | 4 node cluster configured successfully | Execute jps command on console to know whether ResourceManager is up and running | ResourceManager host should be up and running. | ResourceManager host is up and running. |  | TC Created |  | Pass
US039 | US039_TC036 | Environment Testing | To Verify the availabilty of 4 node cluster. (What happens if any node is down for some reason!) | High | 4 node cluster configured successfully | Put down various nodes then verify availability |  |  |  | TC Created |  | Pass
US039 | US039_TC037 | Environment Testing | To Verify that Oozie setup configured successfully through Ambari. | High | Oozie installed successfully | Given I login as admin to Ambari And I navigate to Oozie And I see the "Summary" | Oozie setup should be installed successfully through Ambari. | Oozie setup installed successfully through Ambari. |  | TC Created |  | Pass
US039 | US039_TC038 | Environment Testing | To Verify that Spark setup configured successfully through Ambari. | High | Spark installed successfully | Given I login as admin to Ambari And I navigate to Spark And I see the "Summary" | Spark setup should be installed successfully through Ambari. | Spark setup installed successfully through Ambari. |  | TC Created |  | Pass
US039 | US039_TC039 | Environment Testing | To Verify that Ranger setup configured successfully through Ambari. | High | Ranger installed successfully | Given I login as admin to Ambari And I navigate to Ranger And I see the "Summary" | Ranger setup should be installed successfully through Ambari. | Ranger setup installed successfully through Ambari. |  | TC Created |  | Pass
US039 | US039_TC040 | Environment Testing | Testing the Installation | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for for presenting the list of movies which have been rated with the average ratings by any user | The list of movies which have been rated with the average ratings by any user should be displayed successfully. | The list of movies which have been rated with the average ratings by any user is getting displayed successfully. |  | TC Created |  | Pass
US050: Functional Testing
US024 | US024_TC001 | Functional/Data Testing | Verify that Reference Movie Lens Data has been added to HDFS & Hive successfully. | High | Movie Lens Data has been added to HDFS & Hive successfully. | Count the no of movies, users and ratings from hdfs then count the the no of movies, users and ratings from Hive tables. Counts should be match between hdfs and hive | The count of movies, users and ratings in hdfs and hive should be the same. | The count of movies, users and ratings in hdfs and hive are same.
US024 | US024_TC002 | Functional/Data Testing | Verify that the count of users in HDFS and HIVE are same | High | Movie Lens Data has been added to HDFS & Hive successfully. | For total no of Users: Daily count: hdfs@impetus-i0161:~$ hdfs dfs -cat /user/hdfs/movie_lens_data/users/USERS_20-07-2016 ¦ wc -l 100 Previous day count: hdfs@impetus-i0161:~$ hdfs dfs -cat /user/hdfs/movie_lens_data/users/users.csv ¦ wc -l 247753 Total Users in HDFS: 247753+100=247853 Total users in Hive: hive> select count(*) from users; 247853 | The count of users in hdfs and hive should be the same. | The count of users in hdfs and hive are the same.
US024 | US024_TC003 | Functional/Data Testing | Verify that the count of movies in HDFS and HIVE are same | High | Movie Lens Data has been added to HDFS & Hive successfully. | For total no of Movies: Daily count: hdfs@impetus-i0161:~$ hdfs dfs -cat /user/hdfs/movie_lens_data/movies/MOVIES_20-07-2016 ¦ wc -l 100 Previous day count: hdfs@impetus-i0161:~$ hdfs dfs -cat /user/hdfs/movie_lens_data/movies/movies.csv ¦ wc -l 34208 Total Movies in HDFS: 34208+100=34308 Total movies in Hive: hive> select count(*) from movies; 34308 | The count of movies in hdfs and hive should be the same. | The count of movies in hdfs and hive are the same.
US024 | US024_TC004 | Functional/Data Testing | Verify that the count of ratings in HDFS and HIVE are same | High | Movie Lens Data has been added to HDFS & Hive successfully. | For total no of Ratings: Daily count: hdfs@impetus-i0161:~$ hdfs dfs -cat /user/hdfs/movie_lens_data/ratings/RATINGS_20-07-2016 ¦ wc -l 24760600 Previous day count: hdfs@impetus-i0161:~$ hdfs dfs -cat /user/hdfs/movie_lens_data/ratings/ratings.csv ¦ wc -l 22884377 Total Ratings in HDFS: 24760600+22884377=47644977 Total ratings in Hive: hive> select count(*) from ratings; 47644977 | The count of ratings in hdfs and hive should be the same. | The count of ratings in hdfs and hive are the same.
US024 | US024_TC002 | Functional/Data Testing | Verify the list of all the movies using reference movie lens data. | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting the list of all the movies using reference movie lens data Hive Query: select * from movies; or select count (*)from movies; | The list of all the movies using reference movie lens data should be displayed successfully. | The list of all the movies using reference movie lens data is getting displayed successfully.
US024 | US024_TC003 | Functional/Data Testing | Verify the number of ratings using reference movie lens data. | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting Hive query: select count (*) from ratings or select * from ratings; | The number of ratings using reference movie lens data should be displayed successfully. | The number of ratings using reference movie lens data is getting displayed successfully.
US024 | US024_TC004 | Functional/Data Testing | Verify the List of all the users using reference movie lens data. | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting the List of all the users using reference movie lens data. Hive query: select count (*) from users or select * from users; | The List of all the users using reference movie lens data should be displayed successfully. | The List of all the users using reference movie lens data is getting displayed successfully.
US024 | US024_TC005 | Functional/Data Testing | Verify the list of all the users and the number of ratings they have done for movies. using reference movie lens data. | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting the number of ratings users have done for a movie using reference movie lens data. Hive Query: SELECT users.user_id, users.name, count(ratings.rating) as count FROM users INNER JOIN ratings ON (users.user_id = ratings.user_id) group by users.user_id, users.name; or SELECT users.user_id, users.name, COUNT(ratings.rating) FROM users LEFT OUTER JOIN ratings WHERE users.user_id = ratings.user_id GROUP BY users.user_id, users.name; | The number of ratings users have done for a movie using reference movie lens data should be displayed successfully. | The number of ratings users have done for a movie using reference movie lens data is getting displayed successfully.
US024 | US024_TC006 | Functional/Data Testing | Verify the list of all the Movie IDs which have been rated (Movie Id with at least one user rating it). | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting all Movie IDs which have been rated are listed using reference movie lens data. Hive query: For Count: Select movies.movie_id, movies.title from movies where movies.movie_id in (select distinct movie_id from ratings) order by movie_id; For Data: SELECT DISTINCT ratings.movie_id,m.title from ratings LEFT JOIN (select title,movie_id from movies) as m where ratings.movie_id = m.movie_id; | All Movie IDs which have been rated are listed using reference movie lens data should be displayed successfully. | All Movie IDs which have been rated are listed using reference movie lens data is getting displayed successfully.
US024 | US024_TC007 | Functional/Data Testing | Verify the list of all the Users who have rated the movies (Users who have rated at least one movie). | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting all the Users who have rated the movies are listed using reference movie lens data. Hive query: select users.user_id, users.name, count(ratings.rating) as cnt FROM users INNER JOIN ratings ON (users.user_id = ratings.user_id) group by users.user_id , users.name; | All the Users who have rated the movies are listed using reference movie lens data should be displayed successfully. | All the Users who have rated the movies are listed using reference movie lens data is getting displayed successfully.
US024 | US024_TC008 | Functional/Data Testing | Verify the list of all the User with the max / min / average ratings they have given against any movie. | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting the list of users who have rated any movie with the max ratings Hive query: select users.user_id, max(ratings.rating) as max_rat, min(ratings.rating) as min_rat, ROUND(avg(ratings.rating),2) as avg_rating FROM users INNER JOIN ratings ON (users.user_id = ratings.user_id) group by users.user_id; | The list of users who have rated any movie with the max ratings should be displayed successfully. | The list of users who have rated any movie with the max ratings is getting displayed successfully.
US024 | US024_TC009 | Functional/Data Testing | Verify the list of users who have rated any movie with the max ratings | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting the list of users who have rated any movie with the max ratings Hive query: SELECT users.user_id, users.name, MAX(ratings.rating) FROM ratings,users where ratings.user_id = users.user_id group by users.user_id, users.name; | The list of users who have rated any movie with the max ratings should be displayed successfully. | The list of users who have rated any movie with the max ratings is getting displayed successfully.
US024 | US024_TC010 | Functional/Data Testing | Verify the list of users who have rated any movie with the min ratings | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting the list of users who have rated any movie with the min ratings Hive query: SELECT users.user_id, users.name, MIN(ratings.rating) FROM ratings,users where ratings.user_id = users.user_id group by users.user_id, users.name; | The list of users who have rated any movie with the min ratings should be displayed successfully. | The list of users who have rated any movie with the min ratings is getting displayed successfully.
US024 | US024_TC011 | Functional/Data Testing | Verify the list of users who have rated any movie with the average ratings | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting the list of users who have rated any movie with the average ratings Hive query: SELECT users.user_id, users.name, ROUND(avg(ratings.rating),2) FROM ratings,users where ratings.user_id = users.user_id group by users.user_id, users.name; | The list of users who have rated any movie with the average ratings should be displayed successfully. | The list of users who have rated any movie with the average ratings is getting displayed successfully.
US024 | US024_TC012 | Functional/Data Testing | Verify the list ofall the Movies with the max / min / average ratings given by any user. | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting the list of movies which have been rated with the max ratings by any user Hive query: SELECT movies.movie_id, movies.title, max(ratings.rating) max_rat, min(ratings.rating) as min_rat, round(avg(ratings.rating),2) as avg_rating FROM movies INNER JOIN ratings ON (movies.movie_id = ratings.movie_id) group by movies.movie_id, movies.title; | The list of movies which have been rated with the max ratings by any user should be displayed successfully. | The list of movies which have been rated with the max ratings by any user is getting displayed successfully.
US024 | US024_TC013 | Functional/Data Testing | Verify the list of movies which have been rated with the max ratings by any user | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting the list of movies which have been rated with the max ratings by any user Hive query: SELECT movies.movie_id, movies.title, max(ratings.rating) max_rat FROM movies INNER JOIN ratings ON (movies.movie_id = ratings.movie_id) group by movies.movie_id, movies.title; | The list of movies which have been rated with the max ratings by any user should be displayed successfully. | The list of movies which have been rated with the max ratings by any user is getting displayed successfully.
US024 | US024_TC014 | Functional/Data Testing | Verify the list of movies which have been rated with the min ratings by any user | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting the list of movies which have been rated with the min ratings by any user Hive query: SELECT movies.movie_id, movies.title, min(ratings.rating) as min_rat FROM movies INNER JOIN ratings ON (movies.movie_id = ratings.movie_id) group by movies.movie_id, movies.title; | The list of movies which have been rated with the min ratings by any user should be displayed successfully. | The list of movies which have been rated with the min ratings by any user is getting displayed successfully.
US024 | US024_TC015 | Functional/Data Testing | Verify the list of movies which have been rated with the average ratings by any user | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for presenting the list of movies which have been rated with the average ratings by any user Hive query: SELECT movies.movie_id, movies.title, round(avg(ratings.rating),2) as avg_rating FROM movies INNER JOIN ratings ON (movies.movie_id = ratings.movie_id) group by movies.movie_id, movies.title; | The list of movies which have been rated with the average ratings by any user should be displayed successfully. | The list of movies which have been rated with the average ratings by any user is getting displayed successfully.
US024 | US024_TC016 | Functional/Data Testing | Verify that user should not able to give more than 5.0 rating points | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for verification: select ratings.user_id , ratings.movie_id , ratings.rating, count(*) from ratings where ratings.rating >5.0 group by ratings.user_id , ratings.movie_id , ratings.rating; | User should not able to give more than 5.0 rating points | Verified that User isnot able to give more than 5.0 rating points
US024 | US024_TC017 | Functional/Data Testing | Verify that user should not able to give less than 0.0 rating points | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for verification: select ratings.user_id , ratings.movie_id , ratings.rating , count(*) from ratings where ratings.rating <0.0 group by ratings.user_id , ratings.movie_id , ratings.rating; | User should not able to give less than 0.0 rating points | Verified that User is not able to give less than 0.0 rating points
US024 | US024_TC018 | Functional/Data Testing | Verify that Rating should be between 0.0 and 5.0 rating points | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for verification: select ratings.user_id , ratings.movie_id , ratings.rating , count(*) from ratings where ratings.rating <0.0 or ratings.rating >5.0 group by ratings.user_id , ratings.movie_id , ratings.rating; and select ratings.user_id , ratings.movie_id , ratings.rating , count(*) from ratings where ratings.rating >0.0 or ratings.rating <5.0 group by ratings.user_id , ratings.movie_id , ratings.rating; | Rating should be between 0.0 and 5.0 rating points | Verified that Rating is be between 0.0 and 5.0 rating points
US024 | US024_TC019 | Functional/Data Testing | Verify that single user can not give rating more than one time for a single movie | High | Movie Lens Data has been added to HDFS & Hive successfully. | Execute hive query for verification: select m.user_id , m.movie_id from (select user_id, movie_id, count (*) cnt from ratings group by user_id, movie_id) as m where m.cnt > 1; | single user can not give rating more than one time for a single movie | Verified that single user can not give rating more than one time for a single movie | [7 empty] | DataTesting_01 | Issue fixed by dev team
US0037: HA Testing
US037 | US037_TC001 | HA Testing | Verify that NameNode host is up and running. | High | Hadoop multi-node cluster with NameNodes configured in Active/Standby state | login as admin to Ambari gui and navigate to HDFS then Active NameNode summary or execute jps command on console to know whether NameNode is up and running | NameNode host should be up and running. | NameNode host is up and running. |  |  | TC Created |  | Pass
US037 | US037_TC002 | HA Testing | Verify that Secondary NameNode host is up and running. | High | Hadoop multi-node cluster with NameNodes configured in Active/Standby state | login as admin to Ambari gui and navigate to HDFS then Standby NameNode summary or execute jps command on console to know whether SNN is up and running | Secondary/Standby NameNode host should be up and running. | Secondary/Standby NameNode host is up and running. |  |  | TC Created |  | Pass
US037 | US037_TC003 | HA Testing | Verify that all DataNodes are up and running | High | Hadoop multi-node cluster with NameNodes configured in Active/Standby state | login as admin to Ambari gui and navigate to HDFS then DataNodes summary or execute jps command on console to know whether DataNodes is up and running | All DataNodes host should be up and live. | All DataNodes hosts are up and live. |  |  | TC Created |  | Pass
US037 | US037_TC004 | HA Testing | Verify that NodeManager are up and running | High | Hadoop multi-node cluster with NameNodes configured in Active/Standby state | Execute jps command on console to know whether NodeManager is up and running | NodeManager host should be up and running. | NodeManager host is up and running. |  |  | TC Created |  | Pass
US037 | US037_TC005 | HA Testing | To verify that ResourceManager are up and running | High | Hadoop multi-node cluster with NameNodes configured in Active/Standby state | Execute jps command on console to know whether ResourceManager is up and running | ResourceManager host should be up and running. | ResourceManager host is up and running. |  |  | TC Created |  | Pass
US037 | US037_TC006 | HA Testing | Verify that Rebalance HDFS tool |  | The Balancer role is normally added (by default) when the HDFS service is installed. If it has not been added, you must add a Balancer role instance in order to rebalance HDFS and to see the Rebalance action. | Initiate an HDFS rebalance from Ambari. 1.In Ambari Web, browse to Services > HDFS > Summary. 2.Select Service Actions, then choose Rebalance HDFS. 3.Enter the Balance Threshold value as a percentage of disk capacity. 4.Click Start to begin the rebalance. 5.You can check rebalance progress or cancel a rebalance in process by opening the Background Operations dialog. | Rebalance HDFS should be finished successfully, the Balancer ran successfully. | Rebalance HDFS should be finished successfully, the Balancer ran successfully. |  |  | TC Created |  | Pass
US037 | US037_TC007 | HA Testing | Verify the Balancer threshold configuration |  | The Balancer has a default threshold of 10%, which ensures that disk usage on each DataNode differs from the overall usage in the cluster by no more than 10%. For example, if overall usage across all the DataNodes in the cluster is 40% of the cluster's total disk-storage capacity, the script ensures that DataNode disk usage is between 30% and 50% of the DataNode disk-storage capacity | To change the threshold: 1.Go to the HDFS service. 2.Click the Configuration tab. 3.Expand the Balancer Default Group category. 4.Set the Rebalancing Threshold property. 5.Click Save Changes to commit the changes. | Balancer threshold configuration successfully completed | Balancer threshold configuration successfully completed |  |  | TC Created |  | Pass
US037 | US037_TC008 | HA Testing | Verify that if Name node is down then Standby node should be able to work as active name node | High | Hadoop multi-node cluster with NameNodes configured in Active/Standby state | Login to Ambari url (http://172.26.60.16:8080/#/login) and stop all services on Active name node (impetus-i0095.impetus.co.in), now Standby name node(impetus-i0203.impetus.co.in) switched as Active name node OR Check the health of the NameNode by command- checkHealth this command should return "Success" | If Name node is down then Standby node should be able to work as active name node | If Name node is down then Standby node is able to work as active name node |  |  | TC Created |  | Pass
US037 | US037_TC009 | HA Testing | Verify that if one data node is down, it should not impact the multinode cluster performance | High | Hadoop multi-node cluster with multiple data nodes | Put down one data node then verify availability | Execute few queries to extract data from the cluster, the query performance should be same before and after or at least correct data should be returned for every query execution | Queris are working fine as expected |  |  | TC Created |  | Pass
US037 | US037_TC010 | HA Testing | Verify that if both of the NameNodes are down at the same time then the cluster is effectively unavailable. | High | NameNode should be configured in cluster | I Login to Ambari url (http://172.26.60.16:8080/#/login) and I stop NameNode and Secondory NameNode | If both of the NameNodes are down at the same time then the cluster should be effectively unavailable. | If both of the NameNodes are down at the same time then the cluster is effectively unavailable. |  |  | TC Created |  | Pass
US037 | US037_TC011 | HA Testing | Verify that the ZKFailoverController (ZKFC) process on each node is running so that one of the NameNodes can be converted to active state. | High | ZKFailoverController configured on each machine | Login to Ambari url (http://172.26.60.16:8080/#/login) Go to NameNode Stop the Zookeeper service on Active and StandBy NameNode Put down the Active NameNode | Secondary/Standby NameNode not be able to replace the active name node | Secondary/Standby NameNode not replaced Active NameNode |  |  | TC Created |  | Pass
US037 | US037_TC012 | HA Testing | JournalNodes testing | High | Hadoop multi-node cluster with NameNodes configured in Active/Standby state | Check the number of JournalNodes dameons in the cluster (minimum there should be 3 JNs) | 3 JNs should be running | 3 JNs are configured and working as expected |  |  | TC Created |  | Pass
US037 | US037_TC013 | HA Testing | Verify that if Name node is down, alerts should be generated for all the services residing/installed on that Name node | High | NameNode should be configured in cluster | I Login to Ambari url (http://172.26.60.16:8080/#/login) and I stop the NameNode and I should see the Alerts for all the services installed on that host/NameNode | alert should be generated as soon as Name node is down | Alerts generated as soon as Name node is down |  |  | TC Created |  | Pass
US0036 : Kerbrose Security Testing:
US036 | US036_TC001 | Kerbrose Security Test | Create priciple and try to authinticate to KDC | High | Kerbrose security installed and enabled | Go to host user should be HDFS user kinint -kt <keytab file path> | principle should be created use this command klist | The output of klist will show the details of the principle created whatever you have initiallsed , it will automatically authinticate the request |  |  |  | TC Created |  | Pass
US036 | US036_TC002 | Kerbrose Security Test | Modify renewable time in kdc.config, once this time pas user should not be able to enter | High | Kerbrose security installed and enabled | Login with user Hive Open the krb5.conf modify the ticket lifetime from 24h (default) change the time to 1h try to login after 1h using same keytab | It will not allow the same keytab to work |  |  |  |  | TC Created |  | Pass
US036 | US036_TC003 | Kerbrose Security Test | get pirinciples to see princleples of all services | High | Kerbrose security installed and enabled | Run kadmin command to list all the principles View individual principles by listing principles for individual components | all the created principles will be visible |  |  |  |  | TC Created |  | Pass
US036 | US036_TC004 | Kerbrose Security Test | check/verify hdfs principles details | High | Kerbrose security installed and enabled | get_policy get_principles | [5 empty] | TC Created |  | Pass
US036 | US036_TC005 | Kerbrose Security Test | Person not registered into KDC should not be allowed to enter any service | High | Kerbrose security installed and enabled | Doc | [5 empty] | TC Created
US036 | US036_TC006 | Kerbrose Security Test | try to create modify folders by other principles tickets | High | Kerbrose security installed and enabled | Doc | [5 empty] | TC Created |  | Pass
US036 | US036_TC007 | Kerbrose Security Test | Disable Kerbrose from the Ambari | High | Kerbrose security installed and enabled | Kerbrose should get disable from the cluster | It will not ask/authenticate any user/service accessing any components | Kerbrose Disabled Successfully |  |  |  | TC Created |  | Pass
US036 | US036_TC008 | Kerbrose Security Test | Once installed re enable Kerbrose security in the hadoop cluster | High | Kerbrose security installed and disabled | Kerbrose should get re-enabled on the cluster | It will not ask/authenticate any user/service accessing any components | Kerbrose Disabled Successfully |  |  |  | TC Created |  | Pass
US0057 : Azkaban workflow for Movies
US0057 | US0057_TC001 | Movie Data | To verify hive quere editor running | High | Hadoop multi-node cluster up and running | Login to Ambari url (http://172.26.60.16:8080/#/login) and run all services | Hadoop multi-node cluster up and running and all services run | Hadoop multi-node cluster up and running and all services run |  |  |  | TC Created |  | Pass
US0057 | US0057_TC002 | Movie Data | To verify DB have some relative data | Low | DB have relatine data | Run query select * from movies | Some movie relative data is display | Some movie relative data is display |  |  |  | TC Created |  | Pass
[6 empty] | Run query select * from ratings | Some movie ratings relative data is display | Some movie ratings relative data is display |  |  |  | TC Created |  | Pass
[6 empty] | Run query select * from users | Some users relative data is display | Some users relative data is display |  |  |  | TC Created |  | Pass
US0057 | US0057_TC003 | movie and movie rating | List all the movies and the number of ratings | high | Relative Data should be in DB | Run query "select movies.movie_id, movies.title, ratings.rating from movies movies join rating ratings on (movies.movie_id = ratings.movie_id) limit 10;" | Relative Data fatch from DB | Relative Data fatch from DB |  |  |  | TC Created |  | Pass
US0057 | US0057_TC004 | movie and its rating count by user | List all the users and the number of ratings they have done for a movie | high | Relative Data should be in DB | Run query "select movies.movie_id, movies.title, ratings.user_id, count(ratings.user_id) from movies movies join rating ratings on (movies.movie_id = ratings.movie_id) group by movies.movie_id, movies.title, ratings.user_id limit 10;" | Relative Data fatch from DB | Relative Data fatch from DB |  |  |  | TC Created |  | Pass
US0057 | US0057_TC005 | movies rated atleast once | List all the Movie IDs which have been rated (Movie Id with atleast one user rating it) | high | Relative Data should be in DB | Run query "select movies.movie_id, count(ratings.rating) as total from movies movies join rating ratings on (movies.movie_id = ratings.movie_id) group by movies.movie_id limit 10;" | Relative Data fatch from DB | Relative Data fatch from DB |  |  |  | TC Created |  | Pass
US0057 | US0057_TC006 | User who rated the movie at least once | List all the Users who have rated the movies (Users who have rated atleast one movie) | high | Relative Data should be in DB | Run query "select user_id, count(rating) from rating group by user_id having count(rating) >=1 limit 5 ;" | Relative Data fatch from DB | Relative Data fatch from DB |  |  |  | TC Created |  | Pass
US0057 | US0057_TC007 | rating against user ID | List of all the User with the max,min,average ratings they have given against any movie | high | Relative Data should be in DB | Run query "select ratings.user_id, max(ratings.rating),min(ratings.rating),avg(ratings.rating) from movies mivies join rating ratings on (movies.movie_id = ratings.movie_id) group by ratings.user_id limit 5;" | Relative Data fatch from DB | Relative Data fatch from DB |  |  |  | TC Created |  | Pass
US0057 | US0057_TC008 | rating against movie ID | List all the Movies with the max,min,average ratings given by any user | high | Relative Data should be in DB | Run query for Listing all the Movies with the max,min,average ratings given by any user | Relative Data fatch from DB | Relative Data fatch from DB |  |  |  | TC Created |  | Pass
US0056: Oozie Workflow
US0056 | US0056_TC001 | Oozie Workflow Testing | To Verify that Oozie setup configured successfully through Ambari and users are able to access Oozie GUI | High | Oozie installed successfully | Given I login as admin to Ambari And I navigate to Oozie And I see the "Summary" Oozie GUI: http://impetus-i0161.impetus.co.in:11000/oozie?user.name=admin | Oozie setup should be installed successfully through Ambari and users are able to access Oozie GUI | Oozie setup installed successfully through Ambari and users are able to access Oozie GUI |  |  |  | TC Created |  | Pass
US0056 | US0056_TC002 | Oozie Workflow Testing | Verify that the Oozie workflow XML successfully validated | High | Oozie workflow created successfully | Validate Oozie workflow with below command: oozie validate <WorkFlow Path> | Oozie workflow XML should be validated successfully | Oozie workflow XML is validated successfully |  |  |  | TC Created |  | Pass
US0056 | US0056_TC003 | Oozie Workflow Testing | Verify that the Oozie workflow successfully executed | High | Oozie workflow created successfully | Oozie workflow execution command: oozie job --oozie http://impetus-i0161.impetus.co.in:11000/oozie -Doozie.wf.application.path=hdfs://EETeamJ1/user/oozie/oozie-jobs/job-1/movie_ratings_wf.xml -config /home/IMPETUS/omprakash.soni/ActualWF/MovieRating-WF/job.properties -run | Oozie workflow should be executed successfully | Oozie workflow is executed successfully |  |  |  | TC Created |  | Pass
US0056 | US0056_TC004 | Oozie Workflow Testing | Verify the Oozie job status. | High | Oozie workflow created successfully | Oozie job status check command: oozie job -oozie http://impetus-i0161.impetus.co.in:11000/oozie -info <Jobid> | Oozie job status should be verified | Oozie job status verified successfully |  |  |  | TC Created |  | Pass
US0056 | US0056_TC005 | Oozie Workflow Testing | Verify the Hive script mentioned in Oozie workflow: movie_ratings_table_creation.hive | High | Oozie workflow created successfully | Verify HIVE queries used in script: CREATE TABLE IF NOT EXISTS movie_ratings ( movie_id bigint, title String, max_rating float, avg_rating float, min_rating float) COMMENT 'Max min avg rating of any movie.' ROW FORMAT DELIMITED FIELDS TERMINATED BY ',' LINES TERMINATED BY '\n' STORED AS TEXTFILE; | Hive queries should be executed and movie_ratings table should be created successfully | Hive queries executed and movie_ratings table created successfully |  |  |  | TC Created |  | Pass
US0056 | US0056_TC006 | Oozie Workflow Testing | Verify the Hive script mentioned in Oozie workflow: movie_ratings_data_truncate.hive | High | Oozie workflow created successfully | 1.Insert some random data into the movie_ratings table and after the oozie workflow execution verify that random data should be deleted. 2.Verify HIVE queries used in script: truncate table movie_ratings; | Hive queries should be executed and data should be deleted successfully | Hive queries executed and data deleted successfully |  |  |  | TC Created |  | Pass
US0056 | US0056_TC007 | Oozie Workflow Testing | Verify the Hive script mentioned in Oozie workflow: movie_ratings_data_population.hive | High | Oozie workflow created successfully | 1.Chect the count in the movie_ratings table. 2.Verify HIVE queries used in script: insert overwrite table movie_ratings select m.movie_id,m.title,max(r.rating),avg(r.rating),min(r.rating) from movies m, ratings r where m.movie_id=r.movie_id and r.user_id=247753 group by m.movie_id,m.title; 3.Again check the count in the movie_ratings table. | The count in the movie_ratings table should be matching with the distinct movie count of ratings table. | The count in the movie_ratings table is matching with the distinct movie count of ratings table. |  |  |  | TC Created |  | Pass
US0065 : Azkaban workflow for Users
US0065 | US0065_TC001 | Azkaban Workflow testing | Validate HDFS contains the data in all the tables- movies ratings users movie_ratings mov_rating_count user_rating_count | High | Hadoop multinode cluster with HIVE , Azkaban configured | Run query select * from movies | All movies data should be returned | All movies visible |  |  |  |  | TC Created |  | Pass
[6 empty] | Run query select * from ratings | All ratings data should be returned | All ratings visible |  |  |  |  | TC Created |  | Pass
[6 empty] | Run query select * from users | All users data should be returned | All users visible |  |  |  |  | TC Created |  | Pass
US0065 | US0065_TC002 | Azkaban Workflow testing | Validate the HIVE query for Users with min, max, average ratings given against any movie | High | Hadoop multinode cluster with HIVE , Azkaban configured | Open the Ambari GUI Open HIVE View Select database (movie_lense) Execute Query- select user_id, max(rating), min(rating), round(avg(rating),2) from ratings group by user_id; |  | Relative Data fatch from DB |  |  |  |  | TC Created |  | Pass
US0065 | US0065_TC003 | Azkaban Workflow testing | Verify the Hive script mentioned in Azkaban workflow | High | Hadoop multinode cluster with HIVE , Azkaban configured | Hive queries should be executed and user table should be created successfully | Hive queries executed and users table created successfully | Hive queries executed and user table created successfully |  |  |  |  | TC Created |  | Pass
US0065 | US0065_TC004 | Azkaban Workflow testing | Verify that the Azkaban workflow successfully executed | High | Hadoop multinode cluster with HIVE , Azkaban configured | Azkaban workflow execution command: oozie job --oozie http://impetus-i0161.impetus.co.in:11000/oozie -Doozie.wf.application.path=hdfs://EETeamJ1/user/oozie/oozie-jobs/job-1/movie_ratings_wf.xml -config /home/IMPETUS/omprakash.soni/ActualWF/MovieRating-WF/job.properties -run | Azkaban workflow should be executed successfully | Azkaban workflow is executed successfully |  |  |  |  | TC Created |  | Pass
US0065 | US0065_TC005 | Azkaban Workflow testing | Verify the Azkaban job status. | High | Hadoop multinode cluster with HIVE , Azkaban configured | Azkaban job status check command: oozie job -oozie http://impetus-i0161.impetus.co.in:11000/oozie -info <JobId> | Azkaban job status should be verified | Azkaban job status verified successfully |  |  |  |  | TC Created |  | Pass
US0065 | US0065_TC006 | Azkaban Workflow testing | Verify the Hive script mentioned in Azkaban workflow: | High | Hadoop multinode cluster with HIVE , Azkaban configured | 1.Insert some random data into the movie_ratings table and after the oozie workflow execution verify that random data should be deleted. 2.Verify HIVE queries used in script: truncate table movie_ratings; | Hive queries should be executed and data should be deleted successfully | Hive queries executed and data deleted successfully |  |  |  |  | TC Created |  | Pass
US0065 | US0065_TC007 | Azkaban Workflow testing | Verify the Hive script mentioned in Azkaban workflow: | High | Hadoop multinode cluster with HIVE , Azkaban configured | 1.Chect the count in the movie_ratings table. 2.Verify HIVE queries used in script: insert overwrite table movie_ratings select m.movie_id,m.title,max(r.rating),avg(r.rating),min(r.rating) from movies m, ratings r where m.movie_id=r.movie_id and r.user_id=247753 group by m.movie_id,m.title; 3.Again chect the count in the movie_ratings table. | The count in the movie_ratings table should be matching with the distinct movie count of ratings table. | The count in the movie_ratings table is matching with the distinct movie count of ratings table. |  |  |  |  | TC Created |  | Pass
Summary
|  | Pass |  | 86
|  | Fail |  | 0
|  | Not Run |  | 0
|  | Blocked |  | 0
|  | Total TC |  | 87

## QueriesForTestingData
Scenario | QA - Queries | QA Query Result | Dev Query Result | Status | Comments | Rerun Status after getting failed | Creation Status
Verify the total no of movies. | select count (*)from movies; | 34308 total movies |  | Pass |  | Pass | TC Created | functional
Verify the list of movies. | select * from movies; | 34308 row(s) |  | Pass |  | Pass | TC Created
Verify the no of Users. | select count (*)from users; | 247853 total users |  | Pass |  | Pass | TC Created | sprint 6
Verify the list of users. | select * from users; | 247853 |  | Pass |  | Pass | TC Created
Verify the no of ratings. | select count (*) from ratings or select * from ratings; | 47644977 row(s) |  | Pass |  | Pass | TC Created
List all the movies and the number of ratings: | SELECT movies.movie_id, movies.title, count(ratings.movie_id) as count FROM movies INNER JOIN ratings ON (movies.movie_id = ratings.movie_id) group by movies.movie_id ,title; | 151703 The Butterfly Circus (2009) 1 151709 Zero (2015) 1 151711 The 2000 Year Old Man (1975) 1 Time taken: 33.957 seconds, Fetched: 33670 row(s) | 151701 Bloodmoney (2010) 1 151709 Zero (2015) 1 151711 The 2000 Year Old Man (1975) 1 Time taken: 57.402 seconds, Fetched: 33670 row(s) | Pass |  | Pass | TC Created
List all the users and the number of ratings they have done for movies. | SELECT users.user_id, users.name, count(ratings.rating) as count FROM users INNER JOIN ratings ON (users.user_id = ratings.user_id) group by users.user_id, users.name; | 247751 Test User 247751 190 247752 Test User 247752 33 247753 Test User 247753 22 Time taken: 38.68 seconds, Fetched: 247753 row(s) | 247751 Test User 247751 190 247752 Test User 247752 33 247753 Test User 247753 22 Time taken: 35.29 seconds, Fetched: 247753 row(s) | Pass |  | Pass | TC Created
| SELECT users.user_id, users.name, COUNT(ratings.rating) FROM users LEFT OUTER JOIN ratings WHERE users.user_id = ratings.user_id GROUP BY users.user_id, users.name; | 247751 Test User 247751 190 247752 Test User 247752 33 247753 Test User 247753 22 Time taken: 38.74 seconds, Fetched: 247753 row(s) |  | Pass |  | Pass | TC Created
List all the Movie IDs which have been rated (Movie Id with at least one user rating it). | For Count: Select movies.movie_id, movies.title from movies where movies.movie_id in (select distinct movie_id from ratings) order by movie_id; | 151703 The Butterfly Circus (2009) 151709 Zero (2015) 151711 The 2000 Year Old Man (1975) Time taken: 18.89 seconds, Fetched: 33670 row(s) | 151703 The Butterfly Circus (2009) 151709 Zero (2015) 151711 The 2000 Year Old Man (1975) Time taken: 33.59 seconds, Fetched: 33670 row(s) | Pass |  | Pass | TC Created
| For Data: SELECT DISTINCT ratings.movie_id,m.title from ratings LEFT JOIN (select title,movie_id from movies) as m where ratings.movie_id = m.movie_id; | 151703 The Butterfly Circus (2009) 151709 Zero (2015) 151711 The 2000 Year Old Man (1975) Time taken: 21.10 seconds, Fetched: 33670 row(s) |  | Pass |  | Pass | TC Created
List all the Users who have rated the movies (Users who have rated at least one movie). | select users.user_id, users.name, count(ratings.rating) as cnt FROM users INNER JOIN ratings ON (users.user_id = ratings.user_id) group by users.user_id , users.name; | 247751 Test User 247751 190 247752 Test User 247752 33 247753 Test User 247753 22 Time taken: 22.33 seconds, Fetched: 247753 row(s) | 247751 Test User 247751 247752 Test User 247752 247753 Test User 247753 Time taken: 21.49 seconds, Fetched: 247753 row(s) | Pass |  | Pass | TC Created
List all the User with the max / min / average ratings they have given against any movie. | select users.user_id, max(ratings.rating) as max_rat, min(ratings.rating) as min_rat, ROUND(avg(ratings.rating),2) as avg_rating FROM users INNER JOIN ratings ON (users.user_id = ratings.user_id) group by users.user_id; | 247795 4.9 0.1 2.43 247818 5.0 0.1 2.58 247851 4.8 0.2 2.58 Time taken: 819.38 seconds, Fetched: 247853 row(s)) | 247771 4.9 0.4 2.47 247787 5.0 0.0 2.61 247791 4.9 0.1 2.55 Time taken: 64.92 seconds, Fetched: 247853 row(s) | Pass |  | Pass | TC Created
List all the User with the max ratings they have given against any movie. | SELECT users.user_id, users.name, MAX(ratings.rating) FROM ratings,users where ratings.user_id = users.user_id group by users.user_id, users.name; | 247811 Test User 247811 4.8 247845 Test User 247845 5.0 247850 Test User 247850 4.9 Time taken: 74.41 seconds, Fetched: 247853 row(s) |  | Pass |  | Pass | TC Created
List all the User with the min ratings they have given against any movie. | SELECT users.user_id, users.name, MIN(ratings.rating) FROM ratings,users where ratings.user_id = users.user_id group by users.user_id, users.name; | 247755 Test User 247755 0.3 247757 Test User 247757 0.3 247760 Test User 247760 0.0 Time taken: 119.15 seconds, Fetched: 247853 row(s) |  | Pass |  | Pass | TC Created
List all the User with the average ratings they have given against any movie. | SELECT users.user_id, users.name, ROUND(avg(ratings.rating),2) FROM ratings,users where ratings.user_id = users.user_id group by users.user_id, users.name; | 247755 Test User 247755 2.57 247757 Test User 247757 2.54 247760 Test User 247760 2.61 Time taken: 117.69 seconds, Fetched: 247853 row(s) |  | Pass |  | Pass | TC Created
List all the Movies with the max / min / average ratings given by any user. | SELECT movies.movie_id, movies.title, max(ratings.rating) max_rat, min(ratings.rating) as min_rat, round(avg(ratings.rating),2) as avg_rating FROM movies INNER JOIN ratings ON (movies.movie_id = ratings.movie_id) group by movies.movie_id, movies.title; | 151777 Sample Movie 151777 (2016) 5.0 2.0 3.38 151784 Sample Movie 151784 (2016) 3.5 0.0 1.75 151808 Sample Movie 151808 (2016) 3.5 0.0 1.75 Time taken: 116.836 seconds, Fetched: 33770 row(s) | 151809 Sample Movie 151809 (2016) 5.0 3.38 2.0 151810 Sample Movie 151810 (2016) 3.5 1.75 0.0 151811 Sample Movie 151811 (2016) 5.0 3.37 2.0 Time taken: 71.708 seconds, Fetched: 33770 row(s) | Pass |  | Pass | TC Created
List all the Movies with the max ratings given by any user. | SELECT movies.movie_id, movies.title, max(ratings.rating) max_rat FROM movies INNER JOIN ratings ON (movies.movie_id = ratings.movie_id) group by movies.movie_id, movies.title; | 151777 Sample Movie 151777 (2016) 5.0 151784 Sample Movie 151784 (2016) 3.5 151808 Sample Movie 151808 (2016) 3.5 Time taken: 41.639 seconds, Fetched: 33770 row(s) |  | Pass |  | Pass | TC Created
List all the Movies with the min ratings given by any user. | SELECT movies.movie_id, movies.title, min(ratings.rating) as min_rat FROM movies INNER JOIN ratings ON (movies.movie_id = ratings.movie_id) group by movies.movie_id, movies.title; | 151777 Sample Movie 151777 (2016) 2.0 151784 Sample Movie 151784 (2016) 0.0 151808 Sample Movie 151808 (2016) 0.0 Time taken: 99.576 seconds, Fetched: 33770 row(s) |  | Pass |  | Pass | TC Created
List all the Movies with the average ratings given by any user. | SELECT movies.movie_id, movies.title, round(avg(ratings.rating),2) as avg_rating FROM movies INNER JOIN ratings ON (movies.movie_id = ratings.movie_id) group by movies.movie_id, movies.title; | 151777 Sample Movie 151777 (2016) 3.38 151784 Sample Movie 151784 (2016) 1.75 151808 Sample Movie 151808 (2016) 1.75 Time taken: 44.655 seconds, Fetched: 33770 row(s) |  | Pass |  | Pass | TC Created
Verify that user should not able to give more than 5.0 rating points | select ratings.user_id , ratings.movie_id , ratings.rating, count(*) from ratings where ratings.rating >5.0 group by ratings.user_id , ratings.movie_id , ratings.rating; | 0 rows |  | Pass |  | Pass | TC Created
Verify that user should not able to give less than 0.0 rating points | select ratings.user_id , ratings.movie_id , ratings.rating , count(*) from ratings where ratings.rating <0.0 group by ratings.user_id , ratings.movie_id , ratings.rating; | 0 rows |  | Pass |  | Pass | TC Created
Verify that Rating should be between 0.0 and 5.0 rating points | select ratings.user_id , ratings.movie_id , ratings.rating , count(*) from ratings where ratings.rating <0.0 or ratings.rating >5.0 group by ratings.user_id , ratings.movie_id , ratings.rating; | 0 rows |  | Pass |  | Pass | TC Created
| select ratings.user_id , ratings.movie_id , ratings.rating , count(*) from ratings where ratings.rating >0.0 or ratings.rating <5.0 group by ratings.user_id , ratings.movie_id , ratings.rating; | Time taken: 88.485 seconds, Fetched: 47644977 row(s) which is same as total no of ratings. |  | Pass |  | Pass | TC Created
Verify that single user can not give rating more than one time for a single movie | select m.user_id , m.movie_id from (select user_id, movie_id, count (*) cnt from ratings group by user_id, movie_id) as m where m.cnt > 1; | 0 rows |  | Fail | Issue fixed by dev by removing dublicate data. | Pass | TC Created
|  |  | Pass |  | 24
|  |  | Fail |  | 0
|  |  | Not Run |  | 0
|  |  | Blocked |  | 0
|  |  | Total TC |  | 24

## SmokeTestSuit
US 071#: Name Regression Testing |  |  | Test Cycle #Final
Test Scenario # | Test Scenario Name | Test Scenario Steps | Pass/Fail | Env. (Local / Cluster) | Defect # and Severity | Tested by / Test Date / Package # | Remarks | Creation Staus
US071_TC001 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard (by default Metrics tab selected) Then I should see the Dashboard is loading properly with all the thumbnails under Metrices tab Examples: ¦ HDFS Disk Usage ¦ DataNodes Live ¦ ¦ CPU Usage ¦ HDFS Links ¦ ¦ ICluster Load ¦ Memory Usage ¦ ¦ NameNode Heap ¦ Network Usage ¦ ¦ ResourceManager Uptime ¦ NameNode CPU WIO ¦ | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC002 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard (by default Metrics tab selected) And I modify the time from default to some other value Then I should see the Dashboard thumbnails should get updated with the time | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC003 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard (by default Metrics tab selected) And I select the Heatmaps tab And I see Host Disk Space Used % (by default) And I update metric from Select Metric drop down Then I should see the heatmap and the metric updated with the updated value | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC004 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard (by default Metrics tab selected) And I select the Heatmaps tab And I see Host Disk Space Used % (by default) And I update Maximum % Then I should see the heatmap colour coading should get updated as per the percentage value | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC005 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard (by default Metrics tab selected) And I select the Config History tab Then I should see the Service, Config Group etc | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC006 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard (by default Metrics tab selected) And I see all the services installed on hadoop cluster with "Green" arrow Then I should see all the services on the left pan like- HDFS, MapReduce2, YARN, Tez, Hive, Pig, Oozie, Zookeeper, Ambari Metrics, Kerbrose, Ranger, SmartSense, Spark | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC007 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on HDFS link When I am on Summary tab of HDFS Then on Summary page I should see summary of various HDFS components in Green/Started state Values: Standby_NameNode ¦ ZKFailoverController ¦ ActiveNameNode ¦ DataNodes ¦ DataNodes Status ¦ Journal Nodes ¦ NFSGateways | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC008 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on HDFS link When I click on Heatmaps tab Then I should see HeatMap graph loaded for the default metric successfully | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC009 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on HDFS link When I click on Configs tab Then I should see Configs page loaded successfully | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC010 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on HDFS link And on HDFS summary page I click on Service Actions button And I see various Service Actions When I click on Stop HDFS should stop | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC011 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on HDFS link And on HDFS summary page I click on Service Actions button And I see various Service Actions When I click on Stop HDFS should stop status Stopping/Stopped should be visible on HDFS summary page, alerts should be generated if Maintenance mode is not on | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC012 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on HDFS link And on HDFS summary page I click on Service Actions button And I see various Service Actions When I click on Start HDFS Then all HDFS services should Start status Starting/Started should be visible on HDFS summary page | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC013 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on HDFS link And on HDFS summary page I click on Service Actions button And I see various Service Actions When I click on Restart All Then I should see all the services should get restared successfully | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC014 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on HDFS link And on HDFS summary page I click on Service Actions button And I see various Service Actions And I click on Run Service Check And a background operation will start which will check HDFS service When I click on Ops click on background operation Then I should see the Check HDFS Check successfull | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC015 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on MapReduce2 When I click on MapReduce2 link Then I should see all the summary page loaded succesfully with all the services in Active/Green status | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC016 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on YARN When I click on YARN link Then I should see all the summary page and metrices of YARN loaded succesfully with all the services in Active/Green status | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC017 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on Tez When I click on Tez link Then I should see all the summary page of Tez loaded succesfully with all the services/clients in Active/Green status | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC018 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on Hive When I click on Hive link Then I should see all the summary page of Hive loaded succesfully with all the services/clients in Active/Green status For Example: Hive Metastore ¦ HiveServer ¦ MySQL Server ¦ WebHCat Server ¦ HCat Clients ¦ Hive Clients | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC019 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on Pig When I click on Pig link Then I should see all the summary page of Pig loaded succesfully with all the services/clients in Active/Green status | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC020 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on Oozie When I click on Oozie link Then I should see all the summary page of Oozie loaded succesfully with all the services/clients in Active/Green status | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC021 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on ZooKeeper When I click on ZooKeeper link Then I should see all the summary page of ZooKeeper loaded succesfully with all the services/clients in Active/Green status | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC022 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on Ambari Metrics When I click on Ambari Metrics link Then I should see all the summary page of Ambari Metrics loaded succesfully with all the services/clients in Active/Green status | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC023 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on Kerbrose When I click on Kerbrose link Then I should see all the summary page of Kerbrose loaded succesfully with all the services/clients in Active/Green status | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC024 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on Ranger When I click on Ranger link Then I should see all the summary page of Ranger loaded succesfully with all the services/clients in Active/Green status | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC025 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on SmartSense When I click on SmartSense link Then I should see all the summary page of SmartSense loaded succesfully with all the services/clients in Active/Green status | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC026 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on Spark When I click on Spark link Then I should see all the summary page of Spark loaded succesfully with all the services/clients in Active/Green status | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC027 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on Hosts And I select 1 or All Hosts And I click on Actions When I perform any Action on hosts Then I should see all a background operation should be created and the triggered action should get completed with all the hosts in up and running status | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC028 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on Hosts And I select 1 or All Hosts And I click on Actions When I perform any Action on hosts Then I should see all a background operation should be created and the triggered action should get completed with all the hosts in up and running status Actions like: Start All Components ¦ Stop All Componenets ¦ Restart All Componenets ¦ Turn On Maintenance Mode ¦ Turn Off Maintenance Mode ¦ Set Rack | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC029 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on Hosts And I select few hosts And I navigate to Filtered Hosts or Selected Hosts And I click on Actions When I perform any Action on hosts Then I should see all a background operation should be created and the triggered action should get completed with all the hosts in up and running status Actions like: Start ¦ Stop ¦ Restart ¦ Commission ¦ Decommission | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC030 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on Alerts Then Alerts page should be opened with all the alerts | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC031 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on 9 square icon i.e. views And I click on YARN Queue Manager view Then YARN Queue Manager view should be loaded successfully | Pass | Hadoop Cluster |  | Dilip / 7/20/2016 / none |  | TC Created
US071_TC036 | Environment Sanity | Verify that the Oozie workflow XML successfully validated: Validate Oozie workflow with below command: oozie validate <WorkFlow Path> | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC037 | Environment Sanity | Verify that the Oozie workflow successfully executed Oozie workflow execution command: oozie job --oozie http://impetus-i0161.impetus.co.in:11000/oozie -Doozie.wf.application.path=hdfs://EETeamJ1/user/oozie/oozie-jobs/job-1/movie_ratings_wf.xml -config /home/IMPETUS/omprakash.soni/ActualWF/MovieRating-WF/job.properties -run | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC038 | Environment Sanity | Verify the Oozie job status. Oozie job status check command: oozie job -oozie http://impetus-i0161.impetus.co.in:11000/oozie -info <Jobid> | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC039 | Environment Sanity | Verify the HIVE queries used in Oozie workflow by manually execution 1. movie_ratings_table_creation.hive CREATE TABLE IF NOT EXISTS movie_ratings ( movie_id bigint, title String, max_rating float, avg_rating float, min_rating float) COMMENT 'Max min avg rating of any movie.' ROW FORMAT DELIMITED FIELDS TERMINATED BY ',' LINES TERMINATED BY '\n' STORED AS TEXTFILE; 2.movie_ratings_data_truncate.hive i.Insert some random data into the movie_ratings table and after the oozie workflow execution verify that random data should be deleted. ii.Verify HIVE queries used in script: truncate table movie_ratings; 3. movie_ratings_data_population.hive insert overwrite table movie_ratings select m.movie_id,m.title,max(r.rating),avg(r.rating),min(r.rating) from movies m, ratings r where m.movie_id=r.movie_id and r.user_id=247753 group by m.movie_id,m.title; 4.Again check the count in the movie_ratings table. | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC040 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I hover to Admin And I click on Kerbrose When I am on Kerbrose dashboard page Then at the bottom of the page I should see "All configurations have been addressed" checked , this shows Kerbrose is enabled | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC041 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I hover to Admin And I click on Ranger And I am on Ranger dashboard page And I click on Configs And I click on Ranger Plugin When I Enable <Ranger Plugin> Then it shoud be Enable sucessfully (verify from Ranger Summary page) Ranger Plugins: HDFS Ranger Plugin ¦ YARN Ranger Plugin ¦ Hive Ranger Plugin | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC042 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I hover to Admin And I click on Ranger And I am on Ranger dashboard page And I click on Configs And I click on Ranger Plugin When I Enable <Ranger Plugin> Then it shoud be Disable sucessfully (verify from Ranger Summary page) Ranger Plugins: HDFS Ranger Plugin ¦ YARN Ranger Plugin ¦ Hive Ranger Plugin | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC043 | Environment Sanity | Verify that NameNode host is up and running. login as admin to Ambari gui and navigate to HDFS then Active NameNode summary or execute jps command on console to know whether NameNode is up and running | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC044 | Environment Sanity | Verify that Secondary NameNode host is up and running. login as admin to Ambari gui and navigate to HDFS then Standby NameNode summary or execute jps command on console to know whether SNN is up and running | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC045 | Environment Sanity | Verify that all DataNodes are up and running login as admin to Ambari gui and navigate to HDFS then DataNodes summary or execute jps command on console to know whether DataNodes is up and running | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC046 | Environment Sanity | Verify that Rebalance HDFS tool Initiate an HDFS rebalance from Ambari. 1.In Ambari Web, browse to Services > HDFS > Summary. 2.Select Service Actions, then choose Rebalance HDFS. 3.Enter the Balance Threshold value as a percentage of disk capacity. 4.Click Start to begin the rebalance. 5.You can check rebalance progress or cancel a rebalance in process by opening the Background Operations dialog. | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC047 | Environment Sanity | Verify that if Name node is down then Standby node should be able to work as active name node Login to Ambari url (http://172.26.60.16:8080/#/login) and stop all services on Active name node (impetus-i0095.impetus.co.in), now Standby name node(impetus-i0203.impetus.co.in) switched as Active name node OR Check the health of the NameNode by command- checkHealth this command should return "Success" | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC048 | Environment Sanity | Verify that if both of the NameNodes are down at the same time then the cluster is effectively unavailable. I Login to Ambari url (http://172.26.60.16:8080/#/login) and I stop NameNode and Secondory NameNode If both of the NameNodes are down at the same time then the cluster is effectively unavailable. | Pass | Hadoop Cluster |  |  |  | TC Created
US071_TC050 | Environment Sanity | Given I am admin user And I login to Nagios (URL- http://impetus-i0095.impetus.co.in/nagios/) (nagiosadmin/eeteamj1) And I click on Hosts, Services, Summary, Grid | Pass | Hadoop Cluster |  |  |  | TC Created
Summary
|  | Pass | 45
|  | Fail | 0
|  | Blocked | 0
|  | Not Run | 0
|  | Total TC | 45
spriint 6

## Issues
Defect ID | Description | Linked to User Story | Status | Priority | Sevearity | Comments
DE001 | Verify that single user can not give rating more than one time for a single movie | US050 | Fixed | High | High | Issue fixed by dev team
DE002 | Ganglia home page is not loading, getting this when hitting the Ganglia URL (http://impetus-i0161/ganglia/)- | US071 | Not Fixed | Medium | Low | Very low priority as Nagios is working fine
DE003 | Node not getting stopped | US037 | Fixed | High | High | Issue in Impetus-061 disk
DE004 | Not able to run Azkaban workflow in cluster with Kerbrose security enabled | US067 | Fixed | High | High
DE005 | File View not visible on Ambari GUI | US071 | Not Fixed | Low | Low | [Sudesh] That is expected as Kerberos is enabled and it does not have any key to validate those browser settings. But we can get the view if we directly login to the servers browser, but again here if we need to execute those within browser then we need to either have some third party plugins in Mozilla to make it work with Kerberos.
DE006 | SmartSense View | US072 | Not Fixed | Low | Low | [Sudesh] That is expected as Kerberos is enabled and it does not have any key to validate those browser settings. But we can get the view if we directly login to the servers browser, but again here if we need to execute those within browser then we need to either have some third party plugins in Mozilla to make it work with Kerberos.
DE007 | Hive View not working from Abmbari after enabling Kerbrose | US073 | Not Fixed | Low | Low | [Sudesh] That is expected as Kerberos is enabled and it does not have any key to validate those browser settings. But we can get the view if we directly login to the servers browser, but again here if we need to execute those within browser then we need to either have some third party plugins in Mozilla to make it work with Kerberos.
DE008 | Not able to run Azkaban workflow in cluster with Kerbrose security enabled | US065 | Fixed | High | High
DE009 | 2 out of 4 machines of the cluster down | US070 | Fixed | High | High
DE010 | While testing the environment we are getting few exceptions on Hive view due to which few queries are failing- E090 HDFS020 Could not write file /user/admin/hive/jobs/hive-job-149-2016-06-30_03-55/query.hql [HdfsApiException] This scenario appears when 2 out of 3 Data Nodes are down in the cluster | US071 | Not Fixed | Low | Low | Triage

## TestCases Skipped
US 071#: Name Regression Testing |  |  | Test Cycle #Final
Test Scenario # | Test Scenario Name | Test Scenario Steps | Pass/Fail | Env. (Local / Cluster) | Defect # and Severity | Tested by / Test Date / Package # | Remarks | Creation Staus
US071_TC032 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on 9 square icon i.e. views And I click on File view Then File view should be loaded successfully without any error | Skip | Hadoop Cluster |  | Dilip / 7/20/2016 / none | [Sudesh] That is expected as Kerberos is enabled and it does not have any key to validate those browser settings. But we can get the view if we directly login to the servers browser, but again here if we need to execute those within browser then we need to either have some third party plugins in Mozilla to make it work with Kerberos. | TC Created
US071_TC033 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on 9 square icon i.e. views And I click on Hive view Then Hive view with query manager should be loaded successfully without any error | Skip | Hadoop Cluster |  | Dilip / 7/20/2016 / none | [Sudesh] That is expected as Kerberos is enabled and it does not have any key to validate those browser settings. But we can get the view if we directly login to the servers browser, but again here if we need to execute those within browser then we need to either have some third party plugins in Mozilla to make it work with Kerberos. | TC Created
US071_TC034 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on 9 square icon i.e. views And I click on Hive view And Hive viewwith query manager should be loaded successfully without any error When I execute any query in the query manger (select * from movies) Then query should be executed succesfully with expected results | Skip | Hadoop Cluster |  | Dilip / 7/20/2016 / none | [Sudesh] That is expected as Kerberos is enabled and it does not have any key to validate those browser settings. But we can get the view if we directly login to the servers browser, but again here if we need to execute those within browser then we need to either have some third party plugins in Mozilla to make it work with Kerberos. | TC Created
US071_TC035 | Environment Sanity | Given I am admin user And I login to Ambari (URL-http://172.26.60.16:8080/#/main/dashboard/metrics) And I am on Ambari dashboard And I click on 9 square icon i.e. views And I click on SmartSense view Then SmartSense view should be loaded successfully without any error | Skip | Hadoop Cluster |  | Dilip / 7/20/2016 / none | [Sudesh] That is expected as Kerberos is enabled and it does not have any key to validate those browser settings. But we can get the view if we directly login to the servers browser, but again here if we need to execute those within browser then we need to either have some third party plugins in Mozilla to make it work with Kerberos. | TC Created
US071_TC049 | Environment Sanity | Login to Ganglia using the URL http://impetus-i0161/ganglia/ | Skip | Hadoop Cluster |  |  |  | TC Created
Summary
|  | Pass | 0
|  | Fail | 0
|  | Blocked | 0
|  | Not Run | 0
|  | Total TC | 5
spriint 6