## ScrumTeam
Team Name: | EEJ1
Goal of the Scrum Team: | Hadoop Cluster Setup
Product Owner: | Shirish Bhale
Scrum Master: | Sanchita Mishra
Sprint 1:
Start Date | 2016-05-23
End Date | 2016-05-27
Total days:
Name | Days | Capacity | Available | Planned | Difference
Shashwat Sharma | 5 | 2 | 10 | 10 | 0
Ravi Bhardwaj | 4 | 1.5 | 6 | 6 | 0
Rupika Mahajan | 5 | 2 | 10 | 10 | 0
Dilip Dave | 5 | 1.5 | 7.5 | 7.5 | 0
Pradeep Chand Nailwal | 5 | 2 | 10 | 10 | 0
Sudesh Shettigar | 5 | 2 | 10 | 10 | 0
Santosh Kumar Jha | 5 | 2 | 10 | 10 | 0
Deepti Agrawal | 5 | 2 | 10 | 10 | 0
Om Prakash Soni | 5 | 2 | 10 | 10 | 0
Sanchita Mishra | 5 | 2.5 | 12.5 | 10 | 2.5
Gagandeep Singh Panesar | 5 | 1.5 | 7.5 | 7.5 | 0
Abhishek Parihar | 5 | 2 | 10 | 10 | 0
Total capacity |  |  | 113.5
Sprint 2:
Start Date | 2016-05-30
End Date | 2016-06-03
Total days: | 5
Name | Days | Capacity | Available | Planned | Difference
Shashwat Sharma | 5 | 2 | 10 | 10 | 0
Ravi Bhardwaj |  |  |  | 6 | -6
Rupika Mahajan | 5 | 2 | 10 | 10 | 0
Dilip Dave | 5 | 1.5 | 7.5 | 7.5 | 0
Pradeep Chand Nailwal | 5 | 1 | 5 | 10 | -5
Sudesh Shettigar | 5 | 2 | 10 | 10 | 0
Santosh Kumar Jha | 5 | 2 | 10 | 10 | 0
Deepti Agrawal | 5 | 1.5 | 7.5 | 10 | -2.5
Om Prakash Soni | 5 | 2 | 10 | 10 | 0
Sanchita Mishra | 5 | 2.5 | 12.5 | 10 | 2.5
Gagandeep Singh Panesar | 4 | 2 | 8 | 7.5 | 0.5
Abhishek Parihar | 4 | 2 | 8 | 10 | -2
Total capacity |  |  | 98.5 | 111
Sprint 3
Start Date | 2016-06-06
End Date | 2016-06-17
Total days: | 10
Name | Days | Capacity | Available | Planned | Difference
Shashwat Sharma | 10 | 2 | 20 | 20 | 0
Ravi Bhardwaj | 8 | 1.5 | 12 | 12 | 0
Rupika Mahajan | 10 | 2 | 20 | 20 | 0
Dilip Dave | 6 | 1.5 | 9 | 9 | 0
Pradeep Chand Nailwal | 8 | 1 | 8 | 8 | 0
Sudesh Shettigar | 10 | 2 | 20 | 20 | 0
Santosh Kumar Jha | 10 | 4 | 40 | 40 | 0
Deepti Agrawal | 9 | 2 | 18 | 18 | 0
Om Prakash Soni | 8 | 2 | 16 | 16 | 0
Sanchita Mishra | 10 | 2 | 20 | 20 | 0
Gagandeep Singh Panesar | 10 | 1.5 | 15 | 15 | 0
Abhishek Parihar | 10 | 1 | 10 | 10 | 0
Total capacity |  |  | 208 | 208
Sprint 4
Start Date | 2016-06-20
End Date | 2016-07-01
Total days: | 10
Name | Days | Capacity | Available | Planned | Difference
Shashwat Sharma | 9 | 2 | 18
Ravi Bhardwaj | 9 | 1 | 9
Rupika Mahajan | 10 | 2 | 20
Dilip Dave | 9 | 2 | 18
Pradeep Chand Nailwal | 10 | 1 | 10
Sudesh Shettigar | 10 | 2 | 20 | 20 | 0
Santosh Kumar Jha | 7 | 2 | 14
Deepti Agrawal | 10 | 1.5 | 15
Om Prakash Soni | 10 | 1.5 | 15
Sanchita Mishra | 10 | 2 | 20
Gagandeep Singh Panesar | 10 | 1.5 | 15
Abhishek Parihar | 10 | 1 | 10
Total capacity |  |  | 184
Sprint 5
Start Date | 2016-07-04
End Date | 2016-07-15
Total days: | 10
Name | Days | Capacity | Available | Planned | Difference
Shashwat Sharma | 10 | 2 | 20
Ravi Bhardwaj | 5 | 1.5 | 7
Rupika Mahajan | 8 | 2 | 16
Dilip Dave | 8 | 1.5 | 12
Pradeep Chand Nailwal | 10 | 1 | 10
Sudesh Shettigar | 10 | 2 | 20 | 20 | 0
Santosh Kumar Jha | 10 | 1.5 | 15
Deepti Agrawal | 10 | 1.5 | 15
Om Prakash Soni | 10 | 2 | 20
Sanchita Mishra | 0 | 0 | 0
Gagandeep Singh Panesar | 10 | 1 | 10
Abhishek Parihar | 10 | 1.5 | 15
Total capacity |  |  | 160
Sprint 6
Start Date | 2016-07-18
End Date | 2016-07-22
Total days: | 5
Name | Days | Capacity | Available | Planned | Difference
Shashwat Sharma | 5 | 2 | 10
Ravi Bhardwaj
Rupika Mahajan | 5 | 1.5 | 7.5
Dilip Dave | 5 | 1.5 | 7.5
Pradeep Chand Nailwal | 5 | 1 | 5
Sudesh Shettigar | 5 | 2 | 10
Santosh Kumar Jha | 5 | 1.5 | 7.5
Deepti Agrawal | 5 | 1.5 | 7.5
Om Prakash Soni | 5 | 2 | 10
Sanchita Mishra | 5 | 1 | 5
Gagandeep Singh Panesar | 5 | 1 | 1
Abhishek Parihar | 5 | 2 | 10
Total capacity |  |  | 81

## Product Backlog
User Story | As a(n) [Role/Actor] | I want [Goal/Description] | So That I Can [Benefit] | Done/Acceptance Criteria QA/Business/Architecture/Performance | Priority | Size (in story points) | Impacts (if any) | Dependencies (if any) | Additional Artifacts (if any) | External Dependencies (if any) | Status | Comments | Committed
US001 | As a Dev | I want to set up an Apache Hadoop environment (4 node cluster) and enable HA for Name node, Resource Manager | So that I have environment ready. | Done | 1 | 8
US002 | As a Dev | I want to enable Kerberos | So that I have secure method for authenticating a request for a service in a computer network | Done | 2 | 8
US003 | As a Dev | I want to set up data access using Ranger. | So that I have framework to enable, monitor and manage comprehensive data security across the Hadoop platform. | Done | 3 | 13
US019 | As a User | I want to explore Ambari. | So that I know what components needed for our case study can(not) be deployed using Ambari | Done | 1 | 3
US020 | As a User | I want to explore\configure ELK stack | So that I can do log monitoring. | Done | 2 | 3
US021 | As a Dev | I want to create Sample Application using Pig, Hive , Spark ect. | So that I am able to develop the case study requirement. | Done | 1 | 8
US024 | As a QA | I want to create test cases for sample application and get approval from Dev. | so that I am able to test the sample application | Done | 2 | 5
US025 | As a QA | I want to to create test cases for testing the environment. | So that I am able to test all the environment related parameters. | Done | 2 | 5
US027 | As a User | I want to learn Hadoop / Yarn Technologies | So that I have basic understanding of same | Done | 1 | 3
US028 | As a User | I want to learn PIG | So that I have basic understanding of same | Done | 1 | 3
US029 | As a User | I want to learn Hive | So that I have basic understanding of same | Done | 1 | 3
US030 | As a User | I want to learn Apache Spark | So that I have basic understanding of same | Done | 1 | 3
US031 | As a User | I want to learn Ranger | So that I have basic understanding of same | Done | 1 | 3
US032 | As a User | I want to learn Nagios | So that I have basic understanding of same | Done | 1 | 3
US033 | As a User | I want to learn Gangila | So that I have basic understanding of same | Done | 1 | 3
US034 | As a User | I want to learn ELK | So that I have basic understanding of same | Done | 1 | 3
US035 | As a User | I want to learn Big Data Ecosystem | So that I have basic understanding of same | Done | 1 | 3
US041 | As a Dev | I want to do manual Installation of components like Nagios, Ganglia. | So that I have framework to enable, monitor and manage comprehensive data security across the Hadoop platform. | Done |  | 8
US004 | As a Dev | I want to prepare oozie workflow to list all the movies and the number of ratings | So that I can list all the movies and the number of ratings | Done | 3 | 13
US018 | As a User | I want to explore Nagios and Ganglia to understand its advantages and limitations over each other. | So that I can choose one for our case study as a monitoring tool. | Done | 1 | 5
US039 | As a QA | Environment Testing | So that I am able to ensure the environment is proper setup with all the required configurations | Done |  | 8
US051 | As a Dev | I want to explore refining data using PIG - Exploration for storing refined data from PIG to file. - Exploration for storing refined data from PIG to HIVE. | So that refined data can be processed into HIVE tables. | Done |  | 5
US052 | As a Dev | I want to gather reference movie lens data |  | Done |  | 2
US053 | As a Dev | I want to refine data using PIG - Identify data to be processed into HIVE table. (Fields required from raw data) - Creating HIVE tables for refined data |  | Done |  | 5
US054 | As a Dev | Create cluster through Ambari. Install services like PIG,HIVE through Ambari. Run Hive Scripts on installed Hive. |  | Done |  | 5
US068 | As a Dev | I want to add refined data into HIVE tables | So that data can be processed for further use case computation | Done |  | 2
US016 | As a Dev | I want to add more scnerarios to test cases prepared in Sprint 1, create test artifacts (test strategy doc, test plan) | So that I am aligned with testing process | Done | 3 | 8
US005 | As a Dev | I want to prepare 1 Azkaban workflow to list all the movies and the number of ratings | So that I can list all the movies and the number of ratings. | Done | 3 | 13
US006 | As a Dev | I want to prepare 1 oozie workflow to list all the users and the number of ratings they have done for a movie | So that I can list all the users and the number of ratings they have done for a movie. | Done | 3 | 5
US013 | As a Dev | I want to prepare 1 Azkaban workflow to list all the User with the max,min,average ratings they have given against any movie | So that I can list all the User with the max,min,average ratings they have given against any movie. | Done | 3 | 5
US014 | As a Dev | I want to prepare 1 oozie workflow to list all the Movies with the max,min,average ratings given by any user | So that I can list all the Movies with the max,min,average ratings given by any user. | Done | 3 | 5
US036 | As a QA | I want to do Kerberose Security Testing | To ensure the security is applied to the environment | Done |  | 5
US037 | As a QA | I want to do HA testing | So that I am able to test the failover testing and fault tolerance of the system | Done |  | 5
US044 | As a Dev | I want to explore Hive view in Ambari for Query & Database management | so that user can author and execute queries in the Query Editor | Done |  | 3
US055 | As a Dev | I want to benchmark the Hadoop Environment | So that I can know how the potential performance bottlenecks and resource utilization | Done |  | 13
US057 | As a QA | I want to test Azkaban workflow which list all the movies and the number of ratings | So that I can verify the list of all the movies and the number of ratings | Done |  | 2
US069 | As a Dev | Adding a new host to our cluster and to sync all parameters | So that one of the crashed host could be replaced and all component running could be moved to the new host without affecting the cluster | Done |  | 3
US017 | As a User | I want to set up git and project structure . | So that I have git server ready with my projcet structure | Done | 2 | 3
US040 | As a Dev | I want to understand/setup ELK stack | So that I have ELK setup ready. | Done |  | 5
US010 | As a Dev | I want to prepare 1 oozie workflow to list all the Users who have rated the movies (Users who have rated atleast one movie) | So that I can list all the Users who have rated the movies (Users who have rated atleast one movie). | Done | 3 | 5
US012 | As a Dev | I want to prepare 1 oozie workflow to list all the User with the max,min,average ratings they have given against any movie | So that I can list all the User with the max,min,average ratings they have given against any movie. | Done | 3 | 5
US026 | As a User | I want to commision\decommision a node | So that I can check the impact of that on cluster data. | In progress | 4 | 3
US056 | As a QA | I want to test oozie workflow to list all the Users who have rated the movies (Users who have rated atleast one movie) So that I can list all the Users who have rated the movies (Users who have rated atleast one movie). | So that I can verify the list of all the movies and the number of ratings | Done |  | 2
US065 | As a QA | I want to test Azkaban workflow which list all the User with the max,min,average ratings they have given against any movie | So that I can verify the list all the User with the max,min,average ratings they have given against any movie | Done |  | 2
US066 | As a QA | I want to test oozie workflow which list all the Movies with the max,min,average ratings given by any user | So that I can verify the list all the Movies with the max,min,average ratings given by any user | In progress |  | 2
US022 | As a Dev | I want to create document for Solution architecture for setting up cluster | So that we have one of the project deliverables ready | Done |  | 5
US038 | As a User | Reference use case source code | So that we have one of the project deliverables ready | In progress |  | 3
US042 | As a User | Environment set up document | So that we have one of the project deliverables ready |  |  | 3
US043 | As a User | I want to create monitoring configurations and weekly health reports | So that we have one of the project deliverables ready | In progress |  | 5
US045 | As a Dev | Create Use case for •• List all the Movie IDs which have been rated (Movie Id with at least one user rating it) | So that we have one of the project deliverables ready | Done |  | 1
US047 | As a Dev | Create Use case for • • List all the users and the number of ratings they have done for a movie | So that we have one of the project deliverables ready | In progress |  | 1
US049 | As a User | Installation of Apache Spark and exploration of spark to implement 1 workflow | So that we have one of the project deliverables ready | Done |  | 3
US050 | As a QA | Functional Testing | So that I can verify the HDFS (movie-lens) data | In progress |  | 5
US048 | As a Dev | I want to commit reference project data in Git hub | So that we have one of the project deliverables ready | In progress |  | 3
US070 | As a Dev | Re-setting up of Cluster on account of 2 Nodes disk failure | So that the Enviorment can be available for use | Done |  | 8
US071 | As a QA | Regression Testing | So that all the components and all usecases are working in the hadoop multi-node cluster environment | In progress |  | 5
US072 | As a Dev | I want to finalize solution architecture diagram & document | So that we have one of the project deliverables ready | In-Progress |  | 5
US073 | As a Dev | I want to add data generator tool source code in GIT | So that we have one of the project deliverables ready | In-Progress |  | 5
US074 | As a Dev | 1 Apache Spark workflow implementaion on cluster | So that we have one of the project deliverables ready | In progress |  | 3
282
Total done : 141
In Progress :74
Remaining : 36
|  | Story Points | Story Count | Story Status
|  | 200 | 37 | Done
|  | 69 | 19 | remaining
|  | 44 | 13 | good to have
|  | 313 | 69 | total
Done
In Progress
Must be taken in next Sprint.
Note on A22: Sanchita Mishra: This is epic.

## Sprint0
Sprint Start Date: | 18/5/2016 | 2016-05-23 |  |  | Working Days Left: | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Sprint End Date: | 24/5/2016 | 2016-05-27 |  |  |  |  | Remaining Effort in Hours
Sprint Goals: | [5 empty] | Day 0
Story ID | Task Details | Estimate (Hours) | Owner(s) | Status | Ideal burndown | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Actual burndown | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US035 | Basic Understanding of Big Data Ecosystem |  | Shashwat Sharma | Completed
| Basic Understanding of Big Data Ecosystem |  | Ravi Bhardwaj | Completed
|  |  | Rupika Mahajan | Completed
| Basic Understanding of Big Data Ecosystem |  | Dilip Dave | Completed
| Basic Understanding of Big Data Ecosystem |  | Pradeep Chand Nailwal | Completed
| Basic Understanding of Big Data Ecosystem |  | Sudesh Shettigar | Completed
| Basic Understanding of Big Data Ecosystem |  | Santosh Kumar Jha | Completed
| Basic Understanding of Big Data Ecosystem |  | Deepti Agrawal | Completed
| Basic Understanding of Big Data Ecosystem |  | Sanchita Mishra | Completed
| Basic Understanding of Big Data Ecosystem |  | Gagandeep Singh Panesar | Completed
| Basic Understanding of Big Data Ecosystem |  | Abhishek Parihar | Completed
| Basic Understanding of Big Data Ecosystem |  | Om Prakash Soni | Completed
US027 | Basic Understanding of Hadoop / Yarn Technologies |  | Shashwat Sharma | Completed
| Basic Understanding of Hadoop / Yarn Technologies |  | Ravi Bhardwaj | Completed
| Basic Understanding of Hadoop / Yarn Technologies |  | Rupika Mahajan | Completed
| Basic Understanding of Hadoop / Yarn Technologies |  | Dilip Dave | Completed
| Basic Understanding of Hadoop / Yarn Technologies |  | Pradeep Chand Nailwal | Completed
| Basic Understanding of Hadoop / Yarn Technologies |  | Sudesh Shettigar | Completed
| Basic Understanding of Hadoop / Yarn Technologies |  | Santosh Kumar Jha | Completed
| Basic Understanding of Hadoop / Yarn Technologies |  | Deepti Agrawal | Completed
| Basic Understanding of Hadoop / Yarn Technologies |  | Om Prakash Soni | Completed
| Basic Understanding of Hadoop / Yarn Technologies |  | Sanchita Mishra | Completed
| Basic Understanding of Hadoop / Yarn Technologies |  | Gagandeep Singh Panesar | Completed
| Basic Understanding of Hadoop / Yarn Technologies |  | Abhishek Parihar | Completed
US028 | Basic Understanding of PIG |  | Shashwat Sharma | Completed
| Basic Understanding of PIG |  | Ravi Bhardwaj | Completed
| Basic Understanding of PIG |  | Rupika Mahajan | Completed
| Basic Understanding of PIG |  | Dilip Dave | Completed
| Basic Understanding of PIG |  | Pradeep Chand Nailwal | Completed
| Basic Understanding of PIG |  | Sudesh Shettigar | Completed
| Basic Understanding of PIG |  | Santosh Kumar Jha | Completed
| Basic Understanding of PIG |  | Deepti Agrawal | Completed
| Basic Understanding of PIG |  | Om Prakash Soni | Completed
| Basic Understanding of PIG |  | Sanchita Mishra | Completed
| Basic Understanding of PIG |  | Gagandeep Singh Panesar | Completed
| Basic Understanding of PIG |  | Abhishek Parihar | Completed
US029 | Basic Understanding of Hive |  | Shashwat Sharma | Completed
| Basic Understanding of Hive |  | Ravi Bhardwaj | Completed
| Basic Understanding of Hive |  | Rupika Mahajan | Completed
| Basic Understanding of Hive |  | Dilip Dave | Completed
| Basic Understanding of Hive |  | Pradeep Chand Nailwal | Completed
| Basic Understanding of Hive |  | Sudesh Shettigar | Completed
| Basic Understanding of Hive |  | Santosh Kumar Jha | Completed
| Basic Understanding of Hive |  | Deepti Agrawal | Completed
| Basic Understanding of Hive |  | Om Prakash Soni | Completed
| Basic Understanding of Hive |  | Sanchita Mishra | Completed
| Basic Understanding of Hive |  | Gagandeep Singh Panesar | Completed
| Basic Understanding of Hive |  | Abhishek Parihar | Completed
US030 | Basic Understanding of Apache Spark |  | Shashwat Sharma | Completed
| Basic Understanding of Apache Spark |  | Ravi Bhardwaj | Completed
| Basic Understanding of Apache Spark |  | Rupika Mahajan | Completed
| Basic Understanding of Apache Spark |  | Dilip Dave | Completed
| Basic Understanding of Apache Spark |  | Pradeep Chand Nailwal | Completed
| Basic Understanding of Apache Spark |  | Sudesh Shettigar | Completed
| Basic Understanding of Apache Spark |  | Santosh Kumar Jha | Completed
| Basic Understanding of Apache Spark |  | Deepti Agrawal | Completed
| Basic Understanding of Apache Spark |  | Om Prakash Soni | Completed
| Basic Understanding of Apache Spark |  | Sanchita Mishra | Completed
| Basic Understanding of Apache Spark |  | Gagandeep Singh Panesar | Completed
| Basic Understanding of Apache Spark |  | Abhishek Parihar | Completed
US031 | Basic Understanding of Ranger |  | Shashwat Sharma | Completed
| Basic Understanding of Ranger |  | Ravi Bhardwaj | Completed
| Basic Understanding of Ranger |  | Rupika Mahajan | Completed
| Basic Understanding of Ranger |  | Dilip Dave | Completed
| Basic Understanding of Ranger |  | Pradeep Chand Nailwal | Completed
| Basic Understanding of Ranger |  | Sudesh Shettigar | Completed
| Basic Understanding of Ranger |  | Santosh Kumar Jha | Completed
| Basic Understanding of Ranger |  | Deepti Agrawal | Completed
| Basic Understanding of Ranger |  | Om Prakash Soni | Completed
| Basic Understanding of Ranger |  | Sanchita Mishra | Completed
| Basic Understanding of Ranger |  | Gagandeep Singh Panesar | Completed
| Basic Understanding of Ranger |  | Abhishek Parihar | Completed
US032 | Basic Understanding of Nagios |  | Shashwat Sharma | Completed
| Basic Understanding of Nagios |  | Ravi Bhardwaj | Completed
| Basic Understanding of Nagios |  | Rupika Mahajan | Completed
| Basic Understanding of Nagios |  | Dilip Dave | Completed
| Basic Understanding of Nagios |  | Pradeep Chand Nailwal | Completed
| Basic Understanding of Nagios |  | Sudesh Shettigar | Completed
| Basic Understanding of Nagios |  | Santosh Kumar Jha | Completed
| Basic Understanding of Nagios |  | Deepti Agrawal | Completed
| Basic Understanding of Nagios |  | Om Prakash Soni | Completed
| Basic Understanding of Nagios |  | Sanchita Mishra | Completed
| Basic Understanding of Nagios |  | Gagandeep Singh Panesar | Completed
| Basic Understanding of Nagios |  | Abhishek Parihar | Completed
US033 | Basic Understanding of Gangila |  | Shashwat Sharma | Completed
| Basic Understanding of Gangila |  | Ravi Bhardwaj | Completed
| Basic Understanding of Gangila |  | Rupika Mahajan | Completed
| Basic Understanding of Gangila |  | Dilip Dave | Completed
| Basic Understanding of Gangila |  | Pradeep Chand Nailwal | Completed
| Basic Understanding of Gangila |  | Sudesh Shettigar | Completed
| Basic Understanding of Gangila |  | Santosh Kumar Jha | Completed
| Basic Understanding of Gangila |  | Deepti Agrawal | Completed
| Basic Understanding of Gangila |  | Om Prakash Soni | Completed
| Basic Understanding of Gangila |  | Sanchita Mishra | Completed
| Basic Understanding of Gangila |  | Gagandeep Singh Panesar | Completed
| Basic Understanding of Gangila |  | Abhishek Parihar | Completed
US034 | Basic Understanding of ELK |  | Shashwat Sharma | Completed
| Basic Understanding of ELK |  | Ravi Bhardwaj | Completed
| Basic Understanding of ELK |  | Rupika Mahajan | Completed
| Basic Understanding of ELK |  | Dilip Dave | Completed
| Basic Understanding of ELK |  | Pradeep Chand Nailwal | Completed
| Basic Understanding of ELK |  | Sudesh Shettigar | Completed
| Basic Understanding of ELK |  | Santosh Kumar Jha | Completed
| Basic Understanding of ELK |  | Deepti Agrawal | Completed
| Basic Understanding of ELK |  | Om Prakash Soni | Completed
| Basic Understanding of ELK |  | Sanchita Mishra | Completed
| Basic Understanding of ELK |  | Gagandeep Singh Panesar | Completed
| Basic Understanding of ELK |  | Abhishek Parihar | Completed
Note on F5: :not started , in progress , completed

## Sprint1
Sprint Start Date: | 23/5/2016 | 2016-05-23 |  |  | Working Days Left: | 5 | 4 | 3 | 2 | 1 | 0
Sprint End Date: | 27/5/2016 | 2016-05-27 |  |  |  |  | Remaining Effort in Hours
Sprint Goals: | [5 empty] | Day 0 | 2016-05-23 | 2016-05-24 | 2016-05-25 | 2016-05-26 | 2016-05-27
Story ID | Task Details | Estimate (Hours) | Owner(s) | Status | Ideal burndown | 123.5 | 98.8 | 74.1 | 49.4 | 24.7 | 0
[5 empty] | Actual burndown | 123.5 | 113 | 100.5 | 92 | 80 | 73
US001 | Preparing the server environment for cluster deployment and setting up prerequisites for Ambari Installation | 3 | Shashwat & Sudesh | Done |  | 3 | 2 | 1 | 0 | 0 | 0
| Ambari package download and installation and also setting up local repository for HDP component installation | 3 | Shashwat & Sudesh | Done |  | 3 | 2 | 1 | 1 | 1 | 0
| 4 Node cluster deployment using Ambari along with other components like HDFS, MapReduce, YARN, Tez, Hive,Pig, Oozie, ZooKeeper, Ambari Metrics and Spark etc. | 5 | Shashwat & Sudesh | Not Started |  | 5 | 5 | 5 | 5 | 5 | 5
US002 | Enable Kerberos. | 4 | Shashwat & Sudesh | Not Started |  | 4 | 4 | 4 | 4 | 4 | 4
| Enable HA for Name node, Resource Manager. | 4 | Shashwat & Sudesh | Not Started |  | 4 | 4 | 4 | 4 | 4 | 4
US003 | Installation and configuraion of Ranger | 3 | Shashwat & Sudesh | Not Started |  | 3 | 3 | 3 | 3 | 3 | 3
| Installation and configuration of Nagios | 5 | Shashwat & Sudesh | Not Started |  | 5 | 5 | 5 | 5 | 5 | 5
| Installation and configuration of Ganglia | 5 | Shashwat & Sudesh | Not Started |  | 5 | 5 | 5 | 5 | 5 | 5
| Understanding of ELK and its setup | 8 | Shashwat & Sudesh | Not Started |  | 8 | 8 | 8 | 8 | 8 | 8
US021 | create Sample Application for one work flow. | 10 | Sanchita | blocked |  | 10 | 9 | 8 | 8 | 8 | 8
| create Sample Application for one work flow. | 8 | Deepti | In Progress |  | 8 | 7 | 5 | 5 | 2 | 2
| create Sample Application for one work flow (Hive). - Basic understanding of Hive - Hands on Hive Queries - Creating sample use-case/application | 9 | Gagan | In Progress |  | 9 | 9 | 8 | 8 | 6 | 2
| create Sample Application for one work flow. | 8 | Rupika | Not Started |  | 8 | 8 | 8 | 8 | 8 | 8
| create Sample Application for one work flow. | 9 | Santosh | In Progress |  | 9 | 8 | 7 | 5 | 5 | 5
| create Sample Application for one work flow. -Basic understanding and installation of apache pig -executed sample queries -created a sample script pig script which will join user , movie and rating files | 8 | Om | Completed |  | 8 | 6 | 4 | 2 | 0 | 0
| create Sample Application for one work flow. | 9 | Pradeep | Not Started |  | 9 | 9 | 9 | 9 | 9 | 9
US024 | create test cases for sample application and get approval from Dev. | 5 | Abhishek | Completed |  | 5 | 5 | 5 | 4 | 2 | 0
| create test cases for sample application and get approval from Dev. | 2.5 | Dilip | Completed |  | 2.5 | 1 | 1.5 | 0 | 0 | 0
US025 | create test cases for testing the environment. | 5 | Abhishek | Completed |  | 5 | 3 | 1 | 1 | 0 | 0
| create test cases for testing the environment. | 5 | Dilip | Completed |  | 5 | 5 | 3 | 2 | 0 | 0
| create test cases for testing the environment. | 5 | Ravi | Not Started |  | 5 | 5 | 5 | 5 | 5 | 5
Note on F5: :not started , in progress , completed

## Sprint2
Sprint Start Date: | 2016-05-30 | 2016-05-23 |  |  | Working Days Left: | 5 | 4 | 3 | 2 | 1 | 0
Sprint End Date: | 2016-06-03 | 2016-05-27 |  |  |  |  | Remaining Effort in Hours
Sprint Goals: | [5 empty] | Day 0
Story ID | Task Details | Estimate (Hours) | Owner(s) | Status | Ideal burndown | 94.5 | 75.6 | 56.7 | 37.8 | 18.9 | 0
[5 empty] | Actual burndown | 94.5 | 69 | 51 | 29.5 | 15 | 9
US001 | Preparing the server environment for cluster deployment and setting up prerequisites for Ambari Installation | 3 | Shashwat & Sudesh | Done |  | 0 | 0 | 0 | 0 | 0 | 0
| Ambari package download and installation and also setting up local repository for HDP component installation | 3 | Shashwat & Sudesh | Done |  | 0 | 0 | 0 | 0 | 0 | 0
| 4 Node cluster deployment using Ambari along with other components like HDFS, MapReduce, YARN, Tez, Hive,Pig, Oozie, ZooKeeper, Ambari Metrics and Spark etc. | 5 | Shashwat & Sudesh | Done |  | 5 | 2 | 0 | 0 | 0 | 0
US002 | Enable Kerberos. | 4 | Shashwat & Sudesh | Done |  | 4 | 4 | 4 | 3 | 2 | 0
| Enable HA for Name node, Resource Manager. | 4 | Shashwat & Sudesh | Done |  | 4 | 4 | 3 | 2 | 0 | 0
US003 | Installation and configuraion of Ranger | 3 | Shashwat & Sudesh | Done |  | 3 | 2 | 0 | 0 | 0 | 0
US021 | create Sample Application for one work flow . - Basic understanding of Hive - Hands on Hive Queries - Creating sample use-case/application | 8 | Sanchita | Done |  | 8 | 6 | 4 | 2 | 0 | 0
| Install Ambari on single Ubuntu machine. | 8 | Deepti | Done |  | 8 | 6 | 4 | 1.5 | 0 | 0
| Create Sample Application for Hive (Frequency of books published every year) 1. Hands on Hive Queries (Done) 2. Creating sample use-case/application 2.1 Gather sample data. (Done) 2.2 Create sample tables to hold csv data (Done) 2.3 Extract data from tables for processing Done) 2.4 Do sample computing on gathered data using hive queries.(Done) | 9 | Gagan | Done |  | 9 | 8 | 5 | 2 | 0 | 0
| create Sample Application for one work flow. | 8 | Rupika | In Progress |  | 8 | 8 | 8 | 8 | 8 | 8
| create Sample Application for one work flow. | 9 | Santosh | Done |  | 9 | 7 | 5 | 0 | 0 | 0
| create Sample Application for one work flow. -Basic understanding and installation of apache pig-Done -executed sample queries -created a sample script pig script which will join user , movie and rating files | 8 | Om | Done |  | 8 | 6 | 4 | 2 | 0 | 0
| create Sample Application for one work flow. | 9 | Pradeep | In Progress |  | 9 | 1 | 1 | 1 | 1 | 1
US016 | I want to add more scnerarios to test cases prepared in Sprint 1 | 8 | Abhishek | Done |  | 8 | 6 | 6 | 4 | 2 | 0
| Create Test Plan | 7.5 | Dilip | Done |  | 7.5 | 6 | 5 | 3 | 2 | 0
| Create Test Strategy Doc | 4 | Ravi | Done |  | 4 | 3 | 2 | 1 | 0 | 0
Note on F5: :not started , in progress , completed

## Sprint3
Sprint Start Date: | 2016-06-06 |  |  |  | Working Days Left: | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Sprint End Date: | 2016-06-17 | [5 empty] | Remaining Effort in Hours
Sprint Goals: | 1) Setting up of Nagios & Ganglia 2) Gathering of Reference Movie lens data & process it using PIG & Hive for one workflow 3) Preparing one Oozie workflow 4) Test cases completion for environment verification, oozie, spark & ranger installation |  |  |  |  | Day 0 | 2016-06-06 | 2016-06-07 | 2016-06-08 | 2016-06-09 | 2016-06-10 | 2016-06-13 | 2015-06-14 | 2016-06-15 | 2016-06-16 | 2016-06-17
Story ID | Task Details | Estimate (Hours) | Owner(s) | Status | Ideal burndown | 178 | 160.2 | 142.4 | 124.6 | 106.8 | 89 | 71.2 | 53.4 | 35.6 | 17.8 | 0
[5 empty] | Actual burndown | 178 | 169 | 152 | 135 | 119 | 105 | 78 | 69 | 43 | 28 | 0
US018 | I want to explore Nagios and Ganglia to understand its advantages and limitations over each other. | 4 | Shashwat & Sudesh | Done |  | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US041 | I want to do manual Installation of components like Nagios, Ganglia. | 10 | Shashwat & Sudesh | Done |  | 10 | 10 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Setting up monitor console using Nagios/Ganglia to monitor CPU, Memory, HDP services and parameters | 5 | Shashwat & Sudesh | Done |  | 5 | 5 | 4 | 2 | 2 | 1 | 1 | 1 | 1 | 2 | 0
US051 | I want to explore refining data using PIG - Exploration for storing refined data from PIG to HIVE. | 4 | Om | Done |  | 4 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Exploration for storing refined data from PIG to file. | 4 | Gagandeep | Done |  | 4 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US052 | I want to gather reference movie lens data - Gather reference data for movie lens | 6 | Om & Gagandeep | Done |  | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US053 | I want to refine data using PIG - Identify data to be processed into HIVE table. (Fields required from raw data) - Creating HIVE tables for refined data | 14 | Om & Gagandeep | Done |  | 14 | 14 | 14 | 14 | 14 | 14 | 10 | 6 | 2 | 0 | 0
US068 | I want to add refined data into HIVE tables - Add refined data into HIVE tables. - Verfiy presence of data added into tables (MOVIES, USERS, RATINGS) | 4 | Om & Gagandeep | Done |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0
US039 | Environment Testing -Hadoop Installation -Hive Installation | 10 | Abhishek | Done |  | 10 | 9 | 8 | 7 | 7 | 6 | 5 | 4 | 3 | 2 | 0
| Environment Testing: Pig Installation -Verify the installion of PIG on all components Yarn Installtion Verify the installation of YARN on all components Nagios Installation -Verify the installation of Nagios Agent Ganglia Installation -Verify the installation of Ganglia | 9 | Dilip | Done |  | 9 | 8 | 8 | 7 | 7 | 7 | 5 | 5 | 3 | 2 | 0
| Environment Testing: - Oozie Installation - Spark Installation - Ranger insatallation | 12 | Ravi | Done |  | 12 | 12 | 10 | 10 | 10 | 10 | 8 | 6 | 4 | 2 | 0
US004 | Explore more on oozie workflow | 30 | Sanchita & Santosh | Done |  | 30 | 28 | 26 | 24 | 22 | 16 | 10 | 3 | 0 | 0 | 0
| prepare oozie workflow to list all the movies and the number of ratings | 30 | Sanchita & Santosh | Done |  | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 22 | 18 | 0
1) Creating workflow xml - Done
2) Creating Hive query for table creation -Done
3) Create Hive query for data loading - In Progress
4) Job Configuration - Done
US054 | Create cluster through Ambari. (Done) Install services like PIG,HIVE through Ambari. (Done) Run Hive Scripts on installed Hive. (Done) | 28 | Deepti & Rupika | Done |  | 28 | 26 | 23 | 20 | 17 | 14 | 11 | 9 | 6 | 3 | 0
US021 | Create Movie database and prepare simple hive query. | 8 | Pradeep | Done |  | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 2 | 2 | 1 | 0
Note on F5: :not started , in progress , completed

## Sprint4
Sprint Start Date: | 2016-06-20 | 0 |  |  | Working Days Left: | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Sprint End Date: | 2016-07-01 | 0 |  |  |  |  | Remaining Effort in Hours
Sprint Goals: | 1) Benchmarking of hadoop environment 2) Preparing Azkaban workflows for: - Listing all movies and number of ratings - Listing all the User with Maximum,Minimum and Average ratings they have given against any movie 3) Preparing Oozie workflows for: - Listing all Users who have rated the movies - Listing all the User with the max,min,average ratings they have given against any movie. 4) Test kerberos security 5) Adding a new host to our cluster as replacement to the crashed one and to sync all parameters. 6) Explore hive view in Ambari & execute Hive queries from Ambari. |  |  |  |  | Day 0 | 2016-06-20 | 2016-06-21 | 2016-06-22 | 2016-06-23 | 2016-06-24 | 2016-06-27 | 2016-06-28 | 2016-06-29 | 2016-06-30 | 2016-07-01
Story ID | Task Details | Estimate (Hours) | Owner(s) | Status | Ideal burndown | 185 | 166.5 | 148 | 129.5 | 111 | 92.5 | 74 | 55.5 | 37 | 18.5 | 0
[5 empty] | Actual burndown | 185 | 174 | 158 | 139 | 128 | 116 | 97 | 79 | 67 | 52 | 35
US040 | I want to understand/setup ELK stack | 28 | Sudesh & Pradeep | In Progress |  | 28 | 28 | 27 | 26 | 24 | 22 | 20 | 18 | 18 | 18 | 18
US055 | I want to benchmark the Hadoop Environment -So that I can know how the potential performance bottlenecks and resource utilization | 30 | Shashwat & Dilip | Done |  | 30 | 26 | 24 | 20 | 16 | 14 | 10 | 6 | 4 | 0 | 0
US005 | I want to prepare 1 Azkaban workflow to list all the movies and the number of ratings | 29 | Deepti & Santosh | Done |  | 29 | 26 | 22 | 19 | 17 | 14 | 12 | 10 | 8 | 6 | 0
US006 | I want to prepare 1 oozie workflow to list all the users and the number of ratings they have done for a movie | 20 | Sanchita | Done |  | 20 | 20 | 18 | 14 | 14 | 10 | 10 | 8 | 8 | 4 | 0
US036 | I want to do Kerberose Security Testing -To ensure the security is applied to the environment - Understanding Kerberos security - Perform Kerberose Security Testing | 8 | Dilip & Abhishek | Done |  | 8 | 7 | 6 | 5 | 5 | 5 | 4 | 3 | 2 | 2 | 0
US037 | I want to do HA testing -So that I am able to test the failover testing and fault tolerance of the system - Add test cases for HA testing - Perform HA testing | 8 | Dilip & Abhishek | Done |  | 8 | 7 | 7 | 7 | 6 | 6 | 5 | 4 | 3 | 2 | 0
US044 | I want to explore Hive view in Ambari for Query & Database management - so that user can author and execute queries in the Query Editor | 3 | Gagandeep | Done |  | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US013 | I want to prepare 1 Azkaban workflow to list all the User with : - Maximum ratings they have given against any movie - Minimum ratings they have given against any movie - Average ratings they have given against any movie | 12 | Gagandeep | Done |  | 12 | 12 | 12 | 11 | 11 | 10 | 8 | 6 | 4 | 2 | 0
US012 | I want to prepare 1 oozie workflow to list all the User with the max,min,average ratings they have given against any movie | 20 | Rupika | In- Progress |  | 20 | 20 | 18 | 18 | 16 | 16 | 16 | 16 | 16 | 16 | 16
US069 | Adding a new host to our cluster as replacement to the crashed one and to sync all parameters. | 4 | Sudesh | Done |  | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US014 | As a Dev I want to prepare 1 oozie workflow to list all the Movies with the max,min,average ratings given by any user So that I can list all the Movies with the max,min,average ratings given by any user. | 10 | OM | Done |  | 10 | 9 | 8 | 6 | 6 | 6 | 4 | 2 | 0 | 0 | 0
US010 | I want to prepare 1 oozie workflow to list all the Users who have rated the movies (Users who have rated atleast one movie) So that I can list all the Users who have rated the movies (Users who have rated atleast one movie). | 5 | OM | In- Progress |  | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 1 | 1
US057 | I want to test Azkaban workflow which list all the movies and the number of ratings | 9 | Ravi | Done |  | 9 | 9 | 9 | 8 | 8 | 8 | 4 | 3 | 2 | 1 | 0
Note on F5: :not started , in progress , completed

## Sprint_5
Sprint Start Date: | 2016-07-04 |  | 0 |  |  | Working Days Left: | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
Sprint End Date: | 2016-07-15 |  | 0 |  |  |  |  | Remaining Effort in Hours
Sprint Goals: | 1) Complete the 2 remaining use cases as in requirement doc 2) Demo all the 6 use cases mentioned in the case-study requirement doc 3) Weekly health report of hadoop multi-node cluster 4) ELK Log monitoring | [5 empty] | Day 0 | 2016-07-04 | 2016-07-05 | 2016-07-06 | 2016-07-07 | 2016-07-08 | 2016-07-11 | 2016-07-12 | 2016-07-13 | 2016-07-14 | 2016-07-15
Story ID | Task Details | Size (Story Points) | Estimate (Hours) | Owner(s) | Status | Ideal burndown | 160 | 144 | 128 | 112 | 96 | 80 | 64 | 48 | 32 | 16 | 0
[6 empty] | Actual burndown | 160 | 145 | 131.5 | 112.5 | 96.5 | 91.5 | 89 | 70.5 | 53 | 32.5 | 3
US040 | I want to understand/setup ELK stack | 2 | 18 | Sudesh & Pradeep | Done |  | 18 | 16 | 15 | 10 | 5 | 5 | 5 | 5 | 5 | 3 | 0
ELK had to be setup again as the node on which it was running earlier had disk failure
US012 | I want to prepare 1 oozie workflow to list all the User with the max,min,average ratings they have given against any movie | 5 | 16 | Rupika | Done |  | 16 | 14 | 12 | 10 | 10 | 10 | 8 | 6 | 6 | 6 | 0
US010 | I want to prepare 1 oozie workflow to list all the Users who have rated the movies (Users who have rated atleast one movie) So that I can list all the Users who have rated the movies (Users who have rated atleast one movie). | 5 | 14 | OM & Gagandeep | Done |  | 14 | 12 | 10 | 6 | 3 | 1 | 1 | 1 | 1 | 0 | 0
US049 | #Installation of Apache Spark #Exploration of Apache spark to implement 1 workflow of Spark -Explored Apache Spark -Scala | 3 | 12 | Sudesh & Pradeep | Done |  | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 5 | 3 | 0
US045 | List all the Movie IDs which have been rated (Movie Id with at least one user rating it) (Azkaban) | 1 | 7.5 | Deepti | Done |  | 7.5 | 5.5 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US047 | List all the users and the number of ratings they have done for a movie (Azkaban) | 1 | 15 | Santosh | Done |  | 15 | 13 | 13 | 11 | 9 | 8 | 6.5 | 5 | 3.5 | 2 | 0
US065 | I want to test Azkaban workflow which list all the User with the max,min,average ratings they have given against any movie | 2 | 12 | Dilip | Done |  | 12 | 11 | 10 | 10 | 9 | 8 | 7 | 6 | 4 | 2 | 0
US066 | I want to test oozie workflow which list all the Movies with the max,min,average ratings given by any user | 2 | 7 | Ravi | Spill Over |  | 7 | 6 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
US056 | I want to test oozie workflow to list all the Users who have rated the movies (Users who have rated atleast one movie) So that I can list all the Users who have rated the movies (Users who have rated atleast one movie). | 2 | 15 | Abhishek | Done |  | 15 | 14 | 13 | 12 | 11 | 11 | 10 | 8 | 6 | 4 | 0
US017 | I want to set up git and project structure . | 3 | 7.5 | Deepti | Done |  | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 7.5 | 6.5 | 5.5 | 4.5 | 2.5 | 0
US043 | I want to create monitoring configurations and weekly health reports | 5 | 20 | Shashwat | In - Progress |  | 20 | 18 | 16 | 14 | 12 | 12 | 12 | 10 | 8 | 4
US022 | I want to create document for Solution architecture for setting up cluster | 5 | 16 | OM & Gagandeep | Done |  | 16 | 16 | 14 | 14 | 14 | 14 | 10 | 5 | 5 | 2 | 0
US070 | Re-setting up of Cluster on account of 2 Nodes disk failure. Setup entire 4 node cluster again with Namenode HA,Resource Manger HA and Kerberos enabled | 8 | 10 | Sudesh | Done |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 2 | 1 | 0
Note on G5: :not started , in progress , completed

## Sprint_6
Sprint Start Date: | 2016-07-04 |  | 0 |  |  | Working Days Left: | 10 | 9 | 8 | 7 | 6 | 5
Sprint End Date: | 2016-07-15 |  | 0 |  |  |  |  | Remaining Effort in Hours
Sprint Goals: | [6 empty] | Day 0 | 2016-07-18 | 2016-07-19 | 2016-07-20 | 2016-07-21 | 2016-07-22
Story ID | Task Details | Size (Story Points) | Estimate (Hours) | Owner(s) | Status | Ideal burndown | 44.5 | 40.05 | 35.6 | 31.15 | 26.7 | 22.25
[6 empty] | Actual burndown | 44.5 | 34 | 22 | 8 | 4 | 0
US017 | I want to set up git and project structure -Git repository setup -Case study documentation | 3 | 7.5 | Deepti | Done |  | 7.5 | 5 | 3 | 1 | 0 | 0
US048 | I want to commit reference use case code in Git hub | 3 | 2 | Gagandeep | In Progress |  | 2 | 2 | 2
US026 | I want to commision\decommision a node -Case study documentation |  | 4 | Shashwat | Done |  | 4 | 4 | 2 | 0 | 0 | 0
US050 | Functional Testing -All 6 movie-lense workflows -Data Validation test -Create Test Case documentation | 5 | 10 | Abhishek & Dilip | Done |  | 10 | 5 | 2 | 0 | 0 | 0
US071 | Regression Testing -Environment Testing (Sanity/Smoke Test) -Security Test (Validation of Kerbrose) -Data processing test (Jobs running on Environment) -Ranger implementation test | 5 | 10 | QA Team & Sudesh | In Progress |  | 10 | 10 | 8 | 6 | 4
US066 | I want to test oozie workflow which list all the Movies with the max,min,average ratings given by any user | 2 | 3 | Ravi | In-Progress |  | 3
US072 | I want to finalize solution architecture diagram & document |  | 6 | Om & Gagandeep | In-Progress |  | 6 | 6 | 3 | 1
US073 | I want to add data generator tool source code in GIT |  | 2 | Om | Done |  | 2 | 2 | 2 | 0 | 0 | 0
US074 | Implementation of 1 Apache Spark workflow on cluster |  |  | Pradeep | Not Started
Note on G5: :not started , in progress , completed

## TeamVelocity
Velocity |  |  | Story Count
Sprint # | Plan | Actual | Sprint # | Plan | Actual
0 | 27 | 27 | 0 | 9 | 9
1 | 47 | 24 | 1 | 5 | 0
2 | 47 | 21 | 2 | 5 | 2
3 | 69 | 69 | 3 | 10 | 10
4 | 74 | 59 | 4 | 13 | 10
5 | 36 | 42 | 5 | 12 | 12

## Sprint5 (hidden)
Sprint Start Date: | 2015-04-21 | 0 |  |  | Working Days Left: | 5 | 4 | 3 | 2 | 1 | 0
Sprint End Date: | 2015-04-24 | 0 |  |  |  |  | Remaining Effort in Hours
Sprint Goals: | [5 empty] | Day 0 | 2015-04-20 | 2015-04-21 | 2015-04-22 | 2015-04-23 | 2015-04-24
Story ID | Task Details | Estimate (Hours) | Owner(s) | Status | Ideal burndown | 104 | 83.2 | 62.4 | 41.6 | 20.8 | 0
[5 empty] | Actual burndown | 104 | 81 | 60 | 40 | 30 | 12
US022 | Configuring the Hadoop, Solr, Hive | 4 | Praveen | Stalled |  | 4 | 4 | 4 | 4 | 4 | 4
US060 | Add Cassandra Request at service End | 4 | Amit Pathak | Done |  | 4 | 0 | 0 | 0 | 0 | 0
US061 | Add Logic to add mark transansaction, insert think time and insert loop | 6 | Amit Pathak | Done |  | 6 | 6 | 2 | 0 | 0 | 0
US062 | Add config for Hive, hadoop and Solr from service end | 4 | Amit Pathak | Done |  | 4 | 4 | 4 | 0 | 0 | 0
US063 | Add Request for Hive, hadoop from service end | 8 | Amit Pathak | Done |  | 8 | 8 | 8 | 4 | 4 | 0
US064 | Integrate Cassandra request | 10 | Ankit katiyar | Done |  | 10 | 8 | 6 | 4 | 2 | 0
| Handle right-click functionality dynamically | 8 | Kushalraj Bhandari | Done |  | 8 | 8 | 4 | 4 | 0 | 0
| Integrate Mark transaction,insert loop and think time request | 8 | Ravi Shankar Gupta | impeded on UI |  | 8 | 8 | 6 | 6 | 6 | 6
US065 | Modification in UI look and look | 5 | Manish Manker | Done |  | 5 | 2 | 2 | 2 | 2 | 2
| intergration of request page on right click | 5 | Manish Manker | Done |  | 5 | 2 | 2 | 1 | 0 | 0
| Cassandra Config page Validation | 2 | Nitesh Chandani | Done |  | 2 | 0 | 0 | 0 | 0 | 0
| Create Hive request page and validation | 4 | Nitesh Chandani | Done |  | 4 | 4 | 2 | 0 | 0 | 0 | 4
| intergration of Hive request page on right click | 4 | Nitesh Chandani | Done |  | 4 | 2 | 2 | 2 | 2 | 0
US066 | Open Test case(Service Side) | 12 | Ankit Maheshwari | Done |  | 12 | 9 | 8 | 5 | 4 | 0
US068 | Generating .TCS file pop up to save file | 2 | Amit Pathak | Done |  | 2 | 2 | 2 | 2 | 2 | 0
US067 | Test "Add Cassandra Configuration" functionality | 2 | Deepak Sharma | Done |  | 2 | 2 | 0 | 0 | 0 | 0
| Test "Add Cassandra Configuration" functionality | 2 | Naman Singhal | Done |  | 2 | 2 | 0 | 0 | 0 | 0
US069 | Automation framework | 8 | Naman Singhal | Done |  | 8 | 6 | 4 | 4 | 2 | 0
| Automation framework | 6 | Deepak Sharma | Done |  | 6 | 4 | 4 | 2 | 2 | 0
US097 | Solr test Connection - Service Side Imp | 6 | Ravi Shankar Gupta | Done |  | 6 | 4 | 2 | 0 | 0 | 0
| Ui Integration and Solr installtion | 4 | Ravi Shankar Gupta | Done |  | 4 | 4 | 4 | 4 | 2 | 0
|  | 114 |  |  |  | 114 | 89 | 66 | 44 | 32 | 12
Note on F5: :not started , in progress , completed

## Sprint6 (hidden)
Sprint Start Date: | 2015-04-27 | 0 |  |  | Working Days Left: | 5 | 4 | 3 | 2 | 1 | 0
Sprint End Date: | 2015-05-01 | 0 |  |  |  |  | Remaining Effort in Hours
Sprint Goals: | [5 empty] | Day 0 | 2015-04-27 | 2015-04-28 | 2015-04-29 | 2015-04-30 | 2015-05-01 | Story Points
Story ID | Task Details | Estimate (Hours) | Owner(s) | Status | Ideal burndown | 115 | 92 | 69 | 46 | 23 | 0
[5 empty] | Actual burndown | 115 | 90 | 70 | 53 | 31 | 6
US064 | Integrate Mark transaction,insert loop and think time request | 10 | Ankit katiyar | Done |  | 10 | 8 | 6 | 4 | 2 | 0 | 3
US065 | modification in UI look and feel | 4 | Manish Manker | Done |  | 4 | 3 | 2 | 1 | 0 | 0
| Creating Solr request pages & Mark trasaction page | 6 | Manish Manker | Done |  | 6 | 4 | 3 | 2 | 1 | 0 | 5
US085 | Ability to add Cassendra Configuration | 10 | Deepak Sharma | impeded |  | 10 | 8 | 6 | 4 | 2 | 0 | 3
US089 | Ability to add Cassendra Request | 10 | Naman Singhal | impeded |  | 10 | 8 | 6 | 4 | 2 | 0 | 3
US093 | Ability to Edit Config pages in test case | 6 | Amit Pathak | Done |  | 6 | 2 | 2 | 0 | 0 | 0 | 3
US73 | Ability to Edit Request in test case | 4 | Amit Pathak | Done |  | 4 | 4 | 2 | 0 | 0 | 0 | 3
US74 | Ability to Delete Request in test case | 4 | Amit Pathak | Done |  | 4 | 4 | 4 | 4 | 0 | 0 | 1
US82 | Ability to execute test case independently and completely From Service End | 13 | Ravi Shankar Gupta | Done |  | 13 | 8 | 5 | 3 | 2 | 0 | 3
US94 | Generating Json from serilized object | 2 | Kushalraj Bhandari | Done |  | 2 | 0 | 0 | 0 | 0 | 0 | 5
| Store the Test case JSON into Session | 6 | Kushalraj Bhandari | Done |  | 6 | 6 | 5 | 4 | 4 | 0
| rendering Json data on UI | 10 | Ankit Maheshwari | Done |  | 10 | 9 | 9 | 8 | 6 | 0
US095 | Complete Validation of UI pages | 4 | Nitesh Chandani | Done |  | 4 | 4 | 4 | 5 | 2 | 0 | 3
US097 | Unit test case for Service imple Package | 6 | Praveen | Not Started |  | 6 | 6 | 6 | 6 | 6 | 6 | No updates from Praveen
3
US099 | Create loop screen | 1 | Nitesh Chandani | Done |  | 1 | 0 | 0 | 0 | 0 | 0 | 3
| Create insert think time screen | 3 | Nitesh Chandani | Done |  | 3 | 2 | 0 | 0 | 0 | 0
US101 | Fixing current SprintBug logged by QA | 6 | Amit Pathak | Done |  | 6 | 6 | 4 | 4 | 2 | 0
| Fixing UI component issue | 4 | Palki Arora | Done |  | 4 | 4 | 4 | 4 | 2 | 0 | 5
US102 | Convert alert popup to Web component | 6 | Palki Arora | Done |  | 6 | 4 | 2 | 0 | 0 | 0 | 1
|  | 115 |  |  |  | 115 | 90 | 70 | 53 | 31 | 6
Note on F5: :not started , in progress , completed

## Sprint7 (hidden)
| Sprint Start Date: | 2015-04-05 | 0 |  |  | Working Days Left: | 5 | 4 | 3 | 2 | 1 | 0
| Sprint End Date: | 2015-08-05 | 0 |  |  |  |  | Remaining Effort in Hours
| Sprint Goals: | [5 empty] | Day 0 | 2015-05-04 | 2015-05-05 | 2015-05-06 | 2015-05-07 | 2015-05-08 | Story Points
0 | Story ID | Task Details | Estimate (Hours) | Owner(s) | Status | Ideal burndown | 57 | 45.6 | 34.2 | 22.8 | 11.4 | 0
[6 empty] | Actual burndown | 57 | 47 | 40 | 28 | 19 | 0
| US071 | Ability to Edit/Delete Thinktime in test case | 4 | Amit Pathak | Done |  | 4 | 3 | 2 | 1 | 0 | 0 | 1
| US051 | Ability to view debug logs on the UI from a test run | 3 | Ankit katiyar | Done |  | 3 | 2 | 1 | 0 | 0 | 0 | 2
| US052 | Ability to view debug report on the UI after test run | 3 | Ankit katiyar | Done |  | 3 | 3 | 3 | 2 | 1 | 0 | 2
| US078 | Ability to execute a test case from web with single virtual user and option for multiple iteration from UI | 12 | Ravi Shankar Gupta | done |  | 12 | 12 | 12 | 8 | 4 | 0 | 5
| US0114 | issue fix for solr screen | 1 | Nitesh Chandani | Done |  | 1 | 1 | 1 | 1 | 0 | 0 | 3
|  |  | 2 | Manish Manker | Done |  | 2 | 2 | 1 | 0 | 0 | 0
| US074 | Delete config Request | 7 | Nitesh Chandani | Done |  | 7 | 6 | 6 | 5 | 5 | 0 | 3
| US080 | implementation of insert loop functionality | 10 | Palki Arora | Done |  | 10 | 10 | 8 | 6 | 4 | 0
| US085 | Ability to add Cassandra Configuration | 4 | Deepak Sharma | Done |  | 4 | 2 | 2 | 2 | 2 | 0 | 3
| US089 | Ability to add Cassendra Request | 4 | Naman Singhal | Done |  | 4 | 2 | 2 | 2 | 2 | 0 | 3
| US104 | Bug fixing in sprint 7 | 7 | Amit Pathak | Done |  | 7 | 4 | 2 | 1 | 1 | 0 | 4
|  | Bug fixing in sprint 7 | 8 | Palki Arora | Done |  | 8 | 4 | 4 | 4 | 0 | 0
| US105 | Story to retest bug fixes | 4 | Deepak Sharma | Done |  | 4 | 2 | 0 | 0 | 0 | 0 | 4
|  | Story to retest bug fixes | 4 | Naman Singhal | Done |  | 4 | 2 | 0 | 0 | 0 | 0
| US0107 | alert web-component development and bug fixing | 6 | Palki Arora | Done |  | 6 | 4 | 2 | 0 | 0 | 0
| US0108 | prompt web-component development and bug fixing | 6 | Palki Arora | Done |  | 6 | 4 | 2 | 0 | 0 | 0
| US0109 | alert/prompt web-component code integration. And machine set up | 6 | Palki Arora | Done |  | 6 | 6 | 6 | 4 | 0 | 0
| US0110 | understand the process of GIT | 2 | Palki Arora | Done |  | 2 | 2 | 2 | 2 | 2 | 0
| US0111 | understand the process of SVN | 2 | Palki Arora | Done |  | 2 | 2 | 2 | 2 | 2 | 0
| US0112 | integration of insert loop tree functionalitywith latest code | 4 | Palki Arora | Done |  | 4 | 4 | 4 | 4 | 4 | 0
| US0113 | bug fixing for components | 8 | Palki Arora | Done |  | 8 | 8 | 6 | 6 | 4 | 0
| US065 | Creating Solr request page and validations | 2 | Manish Manker | Done |  | 2 | 2 | 2 | 1 | 0 | 0 | 5
|  | Integrating Solr request page with recorder | 4 | Manish Manker | Done |  | 4 | 4 | 4 | 3 | 2 | 0
| US0115 | Unit Test Cases for CassandraServiceImpl class | 15 | Praveen | Done |  | 15 | 3 | 3 | 3 | 3
| US0116 | Complete Open test case flow | 10 | Ankit Maheshwari | Done |  | 10 | 8 | 8 | 5 | 3 | 0
|  | Integrate the ngStorage with the backend & use it for renderring the information on UI | 8 | Kushalraj Bhandari | Done |  | 8 | 6 | 4 | 2 | 1 | 0
|  |  | 146 |  |  |  | 146 | 102 | 85 | 62 | 39 | 0
Note on F5: :not started , in progress , completed

## Sprint8 (hidden)
| Sprint Start Date: | 2015-11-05 | 0 |  |  | Working Days Left: | 5 | 4 | 3 | 2 | 1 | 0
| Sprint End Date: | 15/05/2015 | 0 |  |  |  |  | Remaining Effort in Hours
| Sprint Goals: | [5 empty] | Day 0 | 2015-05-11 | 2015-05-12 | 2015-05-13 | 2015-05-14 | 2015-05-15
0 | Story ID | Task Details | Estimate (Hours) | Owner(s) | Status | Ideal burndown | 132 | 105.6 | 79.2 | 52.8 | 26.4 | 0 | Story Points
[6 empty] | Actual burndown | 132 | 40 | 26 | 20 | 7 | 0
| US0119 | Change color of application and form buttons and commit code in GIT | 4 | Palki Arora | Done |  | 4 | 3 | 2 | 2 | 1 | 0
| US0120 | bug fixing | 8 | Palki Arora | Done |  | 8 | 7 | 6 | 4 | 2 | 0
| US0121 | Tree Structure Implemetation for Insert loop | 5 | Palki Arora | Done |  | 5 | 5 | 3 | 2 | 1 | 0
| US0122 | Tree Structure Implemetation for mark transection | 4 | Palki Arora | Done |  | 4 | 3 | 2 | 1 | 0 | 0
| US0123 | Tree Structure Implemetation for think time | 4 | Palki Arora | Done |  | 4 | 3 | 2 | 2 | 1 | 0
| US0124 | code commit for Tree Structure Implemetation for Inset loop | 2 | Palki Arora | Done |  | 2 | 2 | 2 | 2 | 1 | 0
| US0125 | code commit for Tree Structure Implemetation for mark transection | 2 | Palki Arora | Done |  | 2 | 2 | 1 | 1 | 0 | 0
| US0126 | code commit for Tree Structure Implemetation for think time | 2 | Palki Arora | Done |  | 2 | 2 | 2 | 1 | 0 | 0
| US0127 | Alignment of radio button in single row | 4 | Palki Arora | Done |  | 4 | 4 | 3 | 2 | 1 | 0
| US0128 | Mockito Test cases for Solr | 9 | Praveen | Done |  | 9 | 9 | 3 | 3 | 0 | 0
| US0129 | Mockito Test cases for Controlelr | 6 | Praveen | Done |  | 6 | 6 | 5 | 4 | 1 | 0
| US118 | Automation script for Cassandra flow and Solr flow | 6 | Deepak Sharma | Done |  | 6 | 6 | 2 | 0 | 0 | 0
|  |  | 6 | Naman Singhal | Done |  | 6 | 6 | 2 | 0 | 0 | 0
| US105 | Story to retest bug fixes | 4 | Deepak Sharma | Done |  | 4 | 4 | 3 | 2 | 1 | 0
|  | Story to retest bug fixes | 4 | Naman Singhal | Done |  | 4 | 4 | 4 | 2 | 1 | 0
| US0128 | issue fix on cassendra page | 2 | Nitesh Chandani | Done |  | 2 | 2 | 1 | 0 | 0 | 0
|  | Addbutton changes | 1 | Nitesh Chandani | Done |  | 1 | 1 | 1 | 1 | 1 | 0
| US0129 | UI for Comment | 2 | Nitesh Chandani | Done |  | 2 | 2 | 2 | 1 | 1 | 0
|  | intigration of comment page | 2 | Nitesh Chandani | Done |  | 2 | 2 | 2 | 2 | 1 | 0
| US0106 | Delete request | 5 | Amit Pathak | Done |  | 5 | 5 | 4 | 3 | 2 | 0
| US0107 | Run test case integration issue & Bug fixing | 10 | Ankit Katiyar | Done |  | 10 | 10 | 6 | 5 | 4 | 0
| US0131 | Scrum related activities | 6 | Kushalraj Bhandari | Done |  | 6 | 6 | 4 | 2 | 2 | 0
| US072 | Ability to define/edit comment Service side | 6 | Amit Pathak | Done |  | 6 | 6 | 2 | 0 | 0 | 0
| US132 | Fixing Bug logged by QA and UI Defect | 6 | Amit Pathak | Done |  | 6 | 6 | 5 | 4 | 2 | 0
| US0133 | Fix refresh and stability issue in Open and Create Test Case flow | 10 | Ankit Maheshwari | Done |  | 10 | 10 | 8 | 6 | 2 | 0
| US0134 | Fix Bub related to Run Test Case | 8 | Ravi Shankar Gupta | Done |  | 8 | 8 | 5 | 4 | 3 | 0
| US098 | Solr test Connection | 4 | Ravi Shankar Gupta | Done |  | 4 | 4 | 3 | 2 | 1 | 0
|  |  | 132 |  |  |  | 132 | 128 | 85 | 58 | 29 | 0
Note on F5: :not started , in progress , completed

## Sprint9 (hidden)
| Sprint Start Date: | 2015-11-18 | 0 |  |  | Working Days Left: | 5 | 4 | 3 | 2 | 1 | 0
| Sprint End Date: | 22/05/2015 | 0 |  |  |  |  | Remaining Effort in Hours
| Sprint Goals: | [5 empty] | Day 0 | 2015-05-18 | 2015-05-19 | 2015-05-20 | 2015-05-21 | 2015-05-22
#REF! | Story ID | Task Details | Estimate (Hours) | Owner(s) | Status | Ideal burndown | 83 | 66.4 | 49.8 | 33.2 | 16.6 | 0 | Story Points
[6 empty] | Actual burndown | 83 | 70 | 55 | 31 | 12 | 0
| US0135 | Solr Run Test Case | 3 | Ankit Maheshwari | Done |  | 10 | 10 | 9 | 7 | 4 | 0
| US0135 | Solr Run Test Case | 3 | Amit Pathak | Done |  | 3 | 0 | 0 | 0 | 0 | 0
| US0136 | Delete test Case | 4 | Amit Pathak | Done |  | 4 | 4 | 4 | 0 | 0 | 0
| US0137 | Two or more users should not be able to update test cases simultaneously | 6 | Ankit Katiyar | Done |  | 6 | 6 | 4 | 2 | 0 | 0
| US0138 | A running test case cannot be deleted | 4 | Ankit Katiyar | Done |  | 6 | 6 | 4 | 2 | 0 | 0
| US0139 | Bug fixing service side | 10 | Ravi Shankar Gupta | Done |  | 10 | 8 | 8 | 4 | 2 | 0
|  | Bug fixing service side | 8 | Amit Pathak | Done |  | 8 | 6 | 4 | 2 | 0 | 0
| US0140 | Bug fixing Ui | 8 | Kushalraj Bhandari | Done |  | 6 | 6 | 4 | 2 | 0 | 0
| US105 | Story to retest bug fixes | 10 | Deepak Sharma | Done |  | 10 | 8 | 6 | 4 | 2 | 0
|  | Story to retest bug fixes | 10 | Naman Singhal | Done |  | 10 | 8 | 6 | 4 | 2 | 0
| US118 | Automation script updation | 5 | Deepak Sharma | Done |  | 5 | 4 | 3 | 2 | 1 | 0
|  | Automation script updation | 5 | Naman Singhal | Done |  | 5 | 4 | 3 | 2 | 1 | 0
|  |  | 76 |  |  |  | 83 | 14 | 13 | 7 | 4 | 0
Note on F5: :not started , in progress , completed

## Impediments
S No | Impediment | Sprint# | Raised On | Raised By | Status | Resolved On | Tracking Notes
1 | Faced issue when installed Ambari 2.1.2 in final installation it failed, as it only provide support to HDP 2.3 not HDP 2.4, we need 4, so uninstalled Ambari 2.1.2 and now installing Ambari 2.2.2. | Sprint-3 | 2016-08-06 | Deepti Agrawal | Resolved | 2016-09-06
2 | Failed to add hadoop components in nagios monitoring list as the validation of configuration file is failing because one of the nodes where kerberose is ruuning isdown with hard disk issue. Raised it with NMG. Need to replace the hard disk. | Sprint-3 | 16/06/2016 | Sudesh | Resolved | 20/06/2016 | Hard disk was replaced and a new OS was installed.
3 | 2 Nodes crashed because of Hard disk issue(OS not booting ) | Sprint-5 | 2016-11-07 | Gagandeep | Resolved | 2016-12-07 | Hard disk was replaced and OS formatted and reinstalled.

## Retrospectives
Sprint 1 | 23-05-2016 to 27-05-2016
Name | What went well | What did not go well | Things to improve upon
Shashwat Sharma
Ravi Bhardwaj
Rupika Mahajan
Dilip Dave | Basic understanding of Hadoop Ecosystem, able to identify test cases for environment tesitng | Test cases review by dev team pending, Use Cases need more refinment | Need more detailed understanding of Hadoop Core before doing actual testing
Pradeep Chand Nailwal
Sudesh Shettigar | Preparing the server environment, Prerequisites setup and installation of ambari-server on Ubutnu15 and Ubuntu14 | Cluster deployment on Ubuntu15 using ambari did not go through as it had issues with python 2.7.9. Had to revert back to Ubuntu14 as Ubuntu 15 was not supported by Hortnworks | Need to read all the requirements throughly before starting the actual deployment.
Santosh Kumar Jha
Deepti Agrawal | Got basic understanding of hadoop, Pig. | Not able to document what we have done and couldn’t follow some of the Scrum processes. | Ever one should follow all the processes of scrum and document the status of their assigned task.
Om Prakash Soni | Completed pig understanding , installation and sample script execution. | Could not start hadoop in yarn mode. | Need to have good understanding of hadoop config parameters.
Sanchita Mishra | Basic understaing of hadoop ecosystem. | Entire team needs to be present in various scrum rituals like backlog grooming , sprint planning meeting, DSM's etc. , which was not the case in Sprint 1. | Need more Team Participation.
Gagandeep Singh Panesar | - Got basic understanding of hadoop ecosystem. | Could not start on actual hadoop macines as the machines were not ready. | Need more understanding on HIVE.
Abhishek Parihar | Basic understaing of hadoop ecosystem. Created Test cases for environment and sample application testing | Test cases review pending | Need more understanding of Hadoop and other tech for creation and execution of test cases
Sprint 2 | 30-05-2016 to 03-06-2016
Name | What went well | What did not go well | Things to improve upon
Shashwat Sharma | 4 Node Cluster Deployment, Ranger installation, Enabling HA on Namenode and Resource Manger and enabling Kerbrose security went fine. | No issues faced in sprint 2 task.
Ravi Bhardwaj | Create Test Strategy Doc
Rupika Mahajan
Dilip Dave | Created Test plan docand shared with team | No issues
Pradeep Chand Nailwal
Sudesh Shettigar | 4 Node Cluster Deployment, Ranger installation, Enabling HA on Namenode and Resource Manger and enabling Kerbrose security went fine. | No issues faced in sprint 2 task.
Santosh Kumar Jha
Deepti Agrawal | Ambari installation has been completed. | Make sure all the team members should attend weekly calls & DSM. | Team should fill the sheet on daily basis, for efforts they put and reaming efforts of their task.
Om Prakash Soni | Learnt Apache Pig details and completed my assigned tasks | No issues. | Need to fill scrum sheet on daily basis
Sanchita Mishra | Team is more involved in sprint 2 as compared to sprint 1. | Better management of task allocation is needed | Still improvement is needed on team participation in DSm and other meetings.
Gagandeep Singh Panesar | Successfully completed one sample workflow using HIVE. | No issues.
Abhishek Parihar | Updated Test cases and shared with team | No issues
Sprint 4
Name | What went well | What did not go well | Things to improve upon
Shashwat Sharma | Installation and setting up of Ganglia Monitoring tool
Ravi Bhardwaj
Rupika Mahajan | Completed writing hive queries for use cases
Dilip Dave
Pradeep Chand Nailwal | Sprint Goal is achieved
Sudesh Shettigar | Installation and setting up of Nagios Monitoring tool | Since one of the host hosting Kerberos had crashed hence could not add all components for rmonitoring | Need to think of a workaround wherever possible for impediments to complete the User Stories so that it doesn’t spill over to the next sprint.
Santosh Kumar Jha
Deepti Agrawal | Sprint Goal is achieved
Om Prakash Soni
Sanchita Mishra | Through better task management and coordination , Team achieved the sprint goals. | Review PPT with incorrect info was sent before Evaluation meeting. | We need to keep scrum sheet updated beforehand to avoid last minute mishap.
Gagandeep Singh Panesar | Reference Movie lens data added successfully into Hive. Also completed Use Case #1 | Wasn’t able to run Hive queries from Ambari Gui. Will work in this sprint for exploration & fixing the same.
Abhishek Parihar | Sprint Goal is achieved
​Om Prakash Soni | Able to execute Pig script and hive sqls over movie data. Succesfully uploaded data into hive after processing through Pig. | ​Could understand the use cases properly. Need more clarification on that.
Sprint 4
Name | What went well | What did not go well | Things to improve upon
Shashwat Sharma | Sprint was successful , team is able to complete their task on weekend.
Ravi Bhardwaj | Able to achieve sprint goals. | Could not provide more time due to important project work
Rupika Mahajan | Sprint goal achieved | Could not provide more time due to important project work | Need to explore more on technologies
Dilip Dave | Cluster was not working well with Kerbrose, but issue addressed on time by Sudesh which prevented Security testing US from spilling over | Delay in few US due to unavailablity of few team members in their respective projects | Dedicate extra time to complete the US in hand irrespective of project/client work
Pradeep Chand Nailwal | Able to achieve sprint goals.
Sudesh Shettigar | ELK Setup was done, but issues observed on configuraiton side | It dealyed the US completion in the sprint, US spilled over
Santosh Kumar Jha | I was able to complete my user stories on time | Could not setup Azkaban on shared cluster due to hive version compatibility
Deepti Agrawal | Team is able to complete Sprint goals |  | Team can Explore more on the technology
Om Prakash Soni | Learnt Oozie setup and job execution | Do not have clear understanding of kerberos so got stuck for a lot of time resolving the security issue. | Need to work for pig action using oozie.
Sanchita Mishra | On leave | On leave | On leave
Gagandeep Singh Panesar | Sprint goal achieved
Abhishek Parihar | Completed HA testing | Delayed due to cluster issue
What did not go well? | Some cluster issues were observerd lately when the sprint was about to end which impacted multiple stories delivery on time
What could be improved? | Need regular monitoring and maintenance of cluster to avoid cluster issues

## What is a user story
What is a user story?
User story is a concise description of a feature narrated by the person requiring a new capability. This is usually an end user or a customer of the system. User Stories focus on Who, What and Why of a feature. They typically follow a simple template: As a <type of user>, I want <some goal> so that <some reason>. A User Story is comprised of three parts described using summary, description and acceptance criteria. • Summary: A brief description of the feature or the name of the story. • Description: Detailed information regarding the feature. It might be a chat history, some feature description, or an image that are marked. Anything that provides more information regarding the feature. • Acceptance Criteria: A set of test that confirms the completeness of the feature. Ideally, this should be written by the customer and could be augmented by a tester. Acceptance criteria may contain technical (architecture/integration), QA (Specific scenarios, impact verification. Automation needs), Operational acceptance criteria. Agile projects, especially Scrum based, use a product backlog, which is a master list of all the functionality to be developed in a product or service. User stories have emerged as the most popular choice for representing items in the product backlog. A user story is incomplete until the discussions about that story occur, and is often best to be thought of as a pointer to the real requirement. User stories could point to a diagram depicting a workflow, a spreadsheet showing how to perform a calculation, or any other artifact the product owner or team desires.
Guidelines
A well written user story should follow the INVEST model. • Independent: As far as possible, care should be taken to avoid introducing dependencies between user stories, Dependencies often lead to complications in prioritization and planning. • Negotiable: They are not written contracts or requirements that the software must implement. They are a short description of functionality, the details of which could be negotiated in a conversation between the product owner and the scrum team. • Valuable to end users: Stories should be written so that their benefits to the end users are apparent. The ideal way to achieve this is to have the customer write the stories. • Estimatable: It should be easy for the developers to estimate or size a user story. Confusions could arise because of lack of domain knowledge or technology or the complexity of the user story. • Small or concise: User stories which are compound and complex stories may be split into multiple smaller stories. If they are too small, multiple tiny stories may be combined into one bigger story. • Testable: Stories must be written so as to be testable.
User story format: As a(n) [Role/Actor] I want [Goal/Description] so that I can [Benefit] A user story should also have defined Acceptance and Evaluation Criteria (Done Criteria)
User story format: As a(n) [Role/Actor] I want [Goal/Description] so that I can [Benefit] User Story below will read as follows: As an Enrollment Representative I want to see a list of new customers enrolled on a quarterly basis, so that I can track the rate of enrollment per quarter.

## Dos and Donts
Dos of User Stories
1. Stories are too small - User stories should be maintained at the right level of size so that it can be slotted in a single sprint. Tiny stories could be problematic in estimating and scheduling. 2. Interdependent Stories - Interdependent stories can be combined to one if they are small. Else it can be separated by following the “slice of cake” method i.e. including functionality from all layers. 3. Gold plating - Gold plating refers to the addition of unnecessary features by the developers. It can be checked during daily status meeting, end of iteration review meetings etc. If there is a dedicated QA in the team, they can also help in identifying gold plating. 4. Too many details - Too much time is being spent gathering details well in advance of a story being implemented. Or, more time is spent writing about stories than talking about them. Writing the stories on notecards can be encouraged which forces story writers to very consciously include fewer details in the stories. 5. Thinking too far ahead - Fundamental to the use of stories is the recognition that for most problems it is impossible to identify all requirements in advance. Right amount of detail for a user story emerges through repeated iterations. 6. Customer has trouble prioritizing - It can be because the story is too big to prioritize or it is not written in a manner that it shows business value to the customer. 7. Customer won’t write and prioritize stories - Customer may not want to take the responsibility, better to let the customer off the hook and take opinion from them and in turn take the ownership of prioritizing. 8. Story writing is teamwork: Leverage the creativity and knowledge of the team and the stakeholders to discover great stories. Invite the team to detail the stories to get them ready for the next sprint planning meeting. 9. Keep your stories simple and concise: Use language that is easy to understand. Avoid confusing and ambiguous terms and use active voice. Focus on what’s important, and leave out non-essential information. Stories are generally most readable when written for a single user. 10. Progressively decompose your stories: Start with big, goal-oriented stories (epics), and derive small, detailed stories that are ready to be transformed into a product increment. 11. Consider grouping user stories into themes: Use themes to organize your stories. Each theme is a group of related stories. Themes make it easier to check for completeness and consistency, they structure your product backlog, and they facilitate prioritization. 12. Size the Story to the horizon, which means writing stories at different levels based on the implementation horizon of the stories. Stories for the next few iterations would be written at sizes that can be planned into those iterations, while more distant stories could be much larger and less precise. 13. On a large project, especially one with many user roles, a better approach would be to begin with identifying user stories specific to a role and then identify the goals that user has for interacting with the software. 14. “Slice the cake” approach should be followed to break larger user stories into smaller ones so that they can fit in one iteration. The stories should provide some level of end-to-end functionality i.e. each story must have a little from each layer. 15. The approach should be to write closed user stories. A closed story is one that finishes with the achievement of a meaningful goal and that allows the user to feel she has accomplished something.
Don'ts of User Stories
16. User stories are not software requirements specifications, use cases or interaction design scenarios. 17. Don’t do splitting of too many stories - Splitting user stories should not become a trait or an easy way out. 18. Don’t forget the acceptance criteria: As you decompose epics into smaller stories, remember to add acceptance criteria. Acceptance criteria complement the story’s narrative, state when the story is complete, and ensure that it is testable. 19. Don’t feel obligated to describe every single aspect of the product as a user story. For instance, user interface design ideas are often best captured in form of paper sketches. 20. Don’t Include UI details too soon - Avoid using UI details early on in the project. Defer talking about the UI in the user stories until the UI is finalized.

## ProductBacklogContinued..
User Story | As a(n) [Role/Actor] | I want [Goal/Description] | So That I Can [Benefit] | Done/Acceptance Criteria QA/Business/Architecture/Performance | Priority | Size (in story points) | Impacts (if any) | Dependencies (if any) | Additional Artifacts (if any) | External Dependencies (if any) | Status | Comments | Committed
US007 | As a Dev | I want to prepare 1 Azkaban workflow to list all the users and the number of ratings they have done for a movie | So that I can list all the users and the number of ratings they have done for a movie. |  | 3 | 5
US008 | As a Dev | I want to prepare 1 oozie workflow to list all the Movie IDs which have been rated (Movie Id with atleast one user rating it) | So that I can list all the Movie IDs which have been rated (Movie Id with atleast one user rating it). |  | 3 | 5
US009 | As a Dev | I want to prepare 1 Azkaban workflow to list all the Movie IDs which have been rated (Movie Id with atleast one user rating it) | So that I can list all the Movie IDs which have been rated (Movie Id with atleast one user rating it). |  | 3 | 5
US011 | As a Dev | I want to prepare 1 Azkaban workflow to list all the Users who have rated the movies (Users who have rated atleast one movie) | So that I can list all the Users who have rated the movies (Users who have rated atleast one movie). |  | 3 | 5
US015 | As a Dev | I want to prepare 1 Azkaban workflow to list all the Movies with the max,min,average ratings given by any user | So that I can list all the Movies with the max,min,average ratings given by any user. |  | 3 | 5
US059 | As a QA | I want to test Azkaban workflow which list all the users and the number of ratings they have done for a movie | So that I can verify the list all the users and the number of ratings they have done for a movie |  |  | 2
US060 | As a QA | I want to test oozie workflow which list all the Movie IDs which have been rated (Movie Id with atleast one user rating it) | So that I can verify the list all the Movie IDs which have been rated (Movie Id with atleast one user rating it) |  |  | 2
US061 | As a QA | I want to test Azkaban workflow which list all the Movie IDs which have been rated (Movie Id with atleast one user rating it) | So that I can verify the list all the Movie IDs which have been rated (Movie Id with atleast one user rating it) |  |  | 2
US063 | As a QA | I want to test Azkaban workflow which list all the Users who have rated the movies (Users who have rated atleast one movie) | So that I can verify the list all the Users who have rated the movies (Users who have rated atleast one movie) |  |  | 2
US067 | As a QA | I want to test Azkaban workflow which list all the Movies with the max,min,average ratings given by any user | So that I can verify the list all the Movies with the max,min,average ratings given by any user |  |  | 2
US023 | As a QA | I want to explore tools for testing data fetched from HDFS. | So that I am able to test the workflows. |  | 1 | 5
US062 | As a QA | I want to test oozie workflow which list all the Users who have rated the movies (Users who have rated atleast one movie) | So that I can verify the list all the Users who have rated the movies (Users who have rated atleast one movie) |  |  | 2
US064 | As a QA | I want to test oozie workflow which list all the User with the max,min,average ratings they have given against any movie | So that I can verify the list all the User with the max,min,average ratings they have given against any movie |  |  | 2
US050
US058